## CBU 2x6015, 14M BN 100010088243
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | 2 X 6015, 1 X 14 M |  |  | CAKUNG |  | MIFA |  | 884800000 | 0 |  |  |  | 2018-01-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[19 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Cakung | [8 empty] | 0% | 0
| Supervisi |  | Handling, Permits, and Formalities |  |  | 150000 | 1 | 2 | person/day | 0.03391% | 300000
| Crane 50T |  | Handling, Permits, and Formalities |  |  | 9500000 | 2 | 1 | Unit/shift | 2.147% | 19000000
| Cakung - Mifa | [8 empty] | 0% | 0
| Trucking Main Unit 6015 |  | Land Transportation | Dolly |  | 105000000 | 2 | 1 | unit/trip | 23.73% | 210000000
| trucking Bucket, stick, counterweight |  | Land Transportation | Lowbed 30T |  | 82500000 | 2 | 1 | unit/trip | 18.65% | 165000000
| trucking boom |  | Land Transportation | Lowbed 20T |  | 80000000 | 2 | 1 | unit/trip | 18.08% | 160000000
| trucking aksesoris |  | Land Transportation | Flat Bed Trailer 40 Feet |  | 62000000 | 4 | 1 | unit/trip | 28.03% | 248000000
| Trucking 14 M |  | Land Transportation | Lowbed 30T |  | 82500000 | 1 | 1 | unit/trip | 9.324% | 82500000
Terms & Condition
| * Terms of delivery | : DTD
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : Dump Truck 30 T
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | : IDR 15.000,-
| * Subject to confirmation | :
| * Cost included | : Ship insurance, fuel.
| * Cost excluded | : Quantity and quality (marine and land) insurance, additional local charges, inspection, storage, demurrage, community issues, taxes,
| * Free Demurrage | : 4 days
| * Demurrage Fee | : Rp 25.000.000
| * Subject to safety max load | :
* Above rates quoted are applicable for general cargo only NOT applicable for DGR, PER, AVI, HUM, and DIP
* Above rates quoted which will be subject to the space availability
* Subject to local charges at origin and destination.
* Rates Quoted excludes other charges, if any, not specified aboveare subject to change with our without prior notice.
* Subject to carrier space and equipment availability.
* Above rates, exclude marine insurance, overtime, urgent delivery and special arrangement / requirements
* Above rates are subject to any duty / taxes at destination
* Rates are subject to any increase on inclusive charges where applicable.
* Rates are subject to any demurrage/additional charges at origin/destination due to shipper/consignee issue
* Charges quoted are inclusive of any regulation/requirement to adhere/complied with Singapore & Destination custom
* For customer's premises that do not permit fumigation, additional transportation & warehouse handling charges are applicable
Term & Condition Demurrage :
Demurrage apply since Vessel is ready at POL based on agreed Laycan
Demurrage apply on daily basis or 24 hours from 00.00 hrs -24.00 hrs
Demurrage remains apply which ever:
1. Port is not available due to queuing process.
2. Jetty's Master approval has not been released.
3. Loading / Unloading cannot be performed due to readiness of the stevedoring company.
4. Loading / Unloading time has exceed its free time.
5. Jetty's Authorized Personel is not available at the office due to National Holiday / Weekend.
6. Low/high tide or
7. Military activities occurance at the port.
COST BUILD UP

## CBU 2X6015+1XD8T
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | 2 X 6015, 1 X 14 M |  |  | CAKUNG |  | MIFA |  | 894300000 | 0 |  |  |  | 2018-01-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[19 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Cakung | [8 empty] | 0% | 0
| Supervisi |  | Handling, Permits, and Formalities |  |  | 150000 | 1 | 2 | person/day | 0.03355% | 300000
| Crane 50T |  | Handling, Permits, and Formalities |  |  | 9500000 | 2 | 1 | Unit/shift | 2.125% | 19000000
| Cakung - Mifa | [8 empty] | 0% | 0
| Trucking Main Unit 6015 |  | Land Transportation | Dolly |  | 105000000 | 2 | 1 | unit/trip | 23.48% | 210000000
| trucking Bucket, stick, counterweight |  | Land Transportation | Lowbed 30T |  | 82500000 | 2 | 1 | unit/trip | 18.45% | 165000000
| trucking boom |  | Land Transportation | Lowbed 20T |  | 80000000 | 2 | 1 | unit/trip | 17.89% | 160000000
| trucking aksesoris |  | Land Transportation | Flat Bed Trailer 40 Feet |  | 62000000 | 4 | 1 | unit/trip | 27.73% | 248000000
| Trucking D8 |  | Land Transportation | Lowbed 40T |  | 92000000 | 1 | 1 | unit/trip | 10.29% | 92000000
Terms & Condition
| * Terms of delivery | : DTD
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : Dump Truck 30 T
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | : IDR 15.000,-
| * Subject to confirmation | :
| * Cost included | : Ship insurance, fuel.
| * Cost excluded | : Quantity and quality (marine and land) insurance, additional local charges, inspection, storage, demurrage, community issues, taxes,
| * Free Demurrage | : 4 days
| * Demurrage Fee | : Rp 25.000.000
| * Subject to safety max load | :
* Above rates quoted are applicable for general cargo only NOT applicable for DGR, PER, AVI, HUM, and DIP
* Above rates quoted which will be subject to the space availability
* Subject to local charges at origin and destination.
* Rates Quoted excludes other charges, if any, not specified aboveare subject to change with our without prior notice.
* Subject to carrier space and equipment availability.
* Above rates, exclude marine insurance, overtime, urgent delivery and special arrangement / requirements
* Above rates are subject to any duty / taxes at destination
* Rates are subject to any increase on inclusive charges where applicable.
* Rates are subject to any demurrage/additional charges at origin/destination due to shipper/consignee issue
* Charges quoted are inclusive of any regulation/requirement to adhere/complied with Singapore & Destination custom
* For customer's premises that do not permit fumigation, additional transportation & warehouse handling charges are applicable
Term & Condition Demurrage :
Demurrage apply since Vessel is ready at POL based on agreed Laycan
Demurrage apply on daily basis or 24 hours from 00.00 hrs -24.00 hrs
Demurrage remains apply which ever:
1. Port is not available due to queuing process.
2. Jetty's Master approval has not been released.
3. Loading / Unloading cannot be performed due to readiness of the stevedoring company.
4. Loading / Unloading time has exceed its free time.
5. Jetty's Authorized Personel is not available at the office due to National Holiday / Weekend.
6. Low/high tide or
7. Military activities occurance at the port.
COST BUILD UP

## CBU Unit support
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | Manitau, Forklift 10T, Genset, Air Compressor |  |  | CAKUNG |  | MIFA |  | 333900000 | 0 |  |  |  | 2018-01-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[19 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| unit support | [8 empty] | 0% | 0
| Manitau |  | Equipment, Tools and Materials |  |  | 60000000 | 1 | 1 | 200 jam | 17.97% | 60000000
| Mob demob Manitau |  | Equipment, Tools and Materials |  |  | 40000000 | 1 | 1 | job | 11.98% | 40000000
| Forklift 10T |  | Equipment, Tools and Materials |  |  | 65000000 | 1 | 1 | 200 jam | 19.47% | 65000000
| Mob demob Forklift 10T |  | Equipment, Tools and Materials |  |  | 40000000 | 1 | 1 | job | 11.98% | 40000000
| Genset 50 KVA |  | Equipment, Tools and Materials |  |  | 15000000 | 1 | 1 | bulan | 4.492% | 15000000
| Mob demob Genset |  | Equipment, Tools and Materials |  |  | 30000000 | 1 | 1 | job | 8.985% | 30000000
| Air Compressor 175 pds airman |  | Equipment, Tools and Materials |  |  | 16000000 | 1 | 1 | bulan | 4.792% | 16000000
| Mob demob air compressor |  | Equipment, Tools and Materials |  |  | 40000000 | 1 | 1 | job | 11.98% | 40000000
| Gaji operator manlift & forklift |  | Handling, Permits, and Formalities |  |  | 200000 | 2 | 31 | person/day | 3.714% | 12400000
| akomodasi operator manlift & forklift |  | Handling, Permits, and Formalities |  |  | 150000 | 2 | 31 | person/day | 2.785% | 9300000
| Penginapan Operator |  | Handling, Permits, and Formalities |  |  | 200000 | 1 | 31 | room/day | 1.857% | 6200000
Terms & Condition
| * Terms of delivery | : DTD
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : Dump Truck 30 T
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | : IDR 15.000,-
| * Subject to confirmation | :
| * Cost included | : Ship insurance, fuel.
| * Cost excluded | : Quantity and quality (marine and land) insurance, additional local charges, inspection, storage, demurrage, community issues, taxes,
| * Free Demurrage | : 4 days
| * Demurrage Fee | : Rp 25.000.000
| * Subject to safety max load | :
* Above rates quoted are applicable for general cargo only NOT applicable for DGR, PER, AVI, HUM, and DIP
* Above rates quoted which will be subject to the space availability
* Subject to local charges at origin and destination.
* Rates Quoted excludes other charges, if any, not specified aboveare subject to change with our without prior notice.
* Subject to carrier space and equipment availability.
* Above rates, exclude marine insurance, overtime, urgent delivery and special arrangement / requirements
* Above rates are subject to any duty / taxes at destination
* Rates are subject to any increase on inclusive charges where applicable.
* Rates are subject to any demurrage/additional charges at origin/destination due to shipper/consignee issue
* Charges quoted are inclusive of any regulation/requirement to adhere/complied with Singapore & Destination custom
* For customer's premises that do not permit fumigation, additional transportation & warehouse handling charges are applicable
Term & Condition Demurrage :
Demurrage apply since Vessel is ready at POL based on agreed Laycan
Demurrage apply on daily basis or 24 hours from 00.00 hrs -24.00 hrs
Demurrage remains apply which ever:
1. Port is not available due to queuing process.
2. Jetty's Master approval has not been released.
3. Loading / Unloading cannot be performed due to readiness of the stevedoring company.
4. Loading / Unloading time has exceed its free time.
5. Jetty's Authorized Personel is not available at the office due to National Holiday / Weekend.
6. Low/high tide or
7. Military activities occurance at the port.
COST BUILD UP

## CBU CRANE Under CK
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | 2 X 6015, 1 X 14 M |  |  | CAKUNG |  | MIFA |  | 871150000 | 0 |  |  |  | 2018-01-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[19 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Mifa | [8 empty] | 0% | 0
| Tiket Pesawat |  | Handling, Permits, and Formalities |  |  | 1800000 | 1 | 2 | person/day | 0.4132% | 3600000
| supervisi |  | Handling, Permits, and Formalities |  |  | 500000 | 1 | 30 | person/day | 1.722% | 15000000
| Rental LV |  | Handling, Permits, and Formalities |  |  | 1500000 | 2 | 31 | person/day | 10.68% | 93000000
| Sewa Crane 50T |  | Handling, Permits, and Formalities |  | min sewa 200 jam | 650000 | 2 | 372 | unit/jam | 55.51% | 483600000
| mobdemob crane |  | Handling, Permits, and Formalities |  |  | 90000000 | 2 | 1 | unit/job | 20.66% | 180000000
| Gaji operator |  | Handling, Permits, and Formalities |  |  | 150000 | 4 | 31 | person/day | 2.135% | 18600000
| Makan Operator |  | Handling, Permits, and Formalities |  |  | 150000 | 4 | 31 | person/day | 2.135% | 18600000
| Penginapan operator |  | Handling, Permits, and Formalities |  |  | 200000 | 3 | 31 | room/day | 2.135% | 18600000
| MCU |  | Handling, Permits, and Formalities |  |  | 2500000 | 8 | 1 | Person/job | 2.296% | 20000000
| Rigger |  | Handling, Permits, and Formalities |  |  | 500000 | 1 | 31 | Person/day | 1.779% | 15500000
| makan rigger |  | Handling, Permits, and Formalities |  |  | 150000 | 1 | 31 | person/day | 0.5338% | 4650000
[10 empty] | 0% | 0
Terms & Condition
| * Terms of delivery | : DTD
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : Dump Truck 30 T
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | : IDR 15.000,-
| * Subject to confirmation | :
| * Cost included | : Ship insurance, fuel.
| * Cost excluded | : Quantity and quality (marine and land) insurance, additional local charges, inspection, storage, demurrage, community issues, taxes,
| * Free Demurrage | : 4 days
| * Demurrage Fee | : Rp 25.000.000
| * Subject to safety max load | :
* Above rates quoted are applicable for general cargo only NOT applicable for DGR, PER, AVI, HUM, and DIP
* Above rates quoted which will be subject to the space availability
* Subject to local charges at origin and destination.
* Rates Quoted excludes other charges, if any, not specified aboveare subject to change with our without prior notice.
* Subject to carrier space and equipment availability.
* Above rates, exclude marine insurance, overtime, urgent delivery and special arrangement / requirements
* Above rates are subject to any duty / taxes at destination
* Rates are subject to any increase on inclusive charges where applicable.
* Rates are subject to any demurrage/additional charges at origin/destination due to shipper/consignee issue
* Charges quoted are inclusive of any regulation/requirement to adhere/complied with Singapore & Destination custom
* For customer's premises that do not permit fumigation, additional transportation & warehouse handling charges are applicable
Term & Condition Demurrage :
Demurrage apply since Vessel is ready at POL based on agreed Laycan
Demurrage apply on daily basis or 24 hours from 00.00 hrs -24.00 hrs
Demurrage remains apply which ever:
1. Port is not available due to queuing process.
2. Jetty's Master approval has not been released.
3. Loading / Unloading cannot be performed due to readiness of the stevedoring company.
4. Loading / Unloading time has exceed its free time.
5. Jetty's Authorized Personel is not available at the office due to National Holiday / Weekend.
6. Low/high tide or
7. Military activities occurance at the port.
COST BUILD UP
Note on I13: 31 hari x 12 jam

## Time frame
Project | Operating Plan | Days |  | November |  |  |  |  | DESEMBER | [30 empty] | JAKARTA
|  |  |  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
Mob 4 x CAT 6015 (CKB CKN - CK MIFA) | CKN
| Loading 2 x 6015 at CKB Cakung | 1 | Days | bar: November 26
CKN - Meulaboh (6015 Trip 1)
| 2 x Trucking Dolly untuk main unit | 19 | Days | bar: November 26 to DESEMBER 14
| 2 x Trucking Lowbed 30 untuk Counterweight, stick, bucket | 15 | Days | bar: November 26 to DESEMBER 10
| 2 x Trucking Lowbed 20 untuk Boom | 15 | Days | bar: November 26 to DESEMBER 10
| 2 x Trucking Trailer 40untuk Track + Accs | 15 | Days | bar: November 26 to DESEMBER 10
| 2 x Trucking Trailer 40untuk Track + Accs | 15 | Days | bar: November 26 to DESEMBER 10
CKN - Meulaboh (14 M)
| Trucking 14M | 15 | Days | bar: November 27 to DESEMBER 11
CKN - Meulaboh (6015 Trip 2)
| 2 x Trucking Dolly untuk main unit | 19 | Days | bar: November 29 to DESEMBER 20
| 2 x Trucking Lowbed 30 untuk Counterweight, stick, bucket | 15 | Days | bar: November 29 to DESEMBER 13
| 2 x Trucking Lowbed 20 untuk Boom | 15 | Days | bar: November 29 to DESEMBER 13
| 2 x Trucking Trailer 40untuk Track + Accs | 15 | Days | bar: November 29 to DESEMBER 13
| 2 x Trucking Trailer 40untuk Track + Accs | 15 | Days | bar: November 29 to DESEMBER 13
CKN - Meulaboh (D8T)
| Trucking D8T | 15 | Days | bar: November 29 to DESEMBER 13
MIFA
| Mob 2 x Crane 50T + unit support | 3 | Days | bar: DESEMBER 6 to DESEMBER 8
| commisioning | 2 | Days | bar: DESEMBER 9 to DESEMBER 10
| Assembly 6015 (1) | 6 | Days | bar: DESEMBER 10 to DESEMBER 15
| Assembly 6015 (2) | 6 | Days | bar: DESEMBER 16 to DESEMBER 21
| Assembly 6015 (3) | 6 | Days | bar: DESEMBER 22 to DESEMBER 27
| Assembly 6015 (4) | 6 | Days | bar: DESEMBER 28 to JAKARTA 2
| Demob Crane | 3 | Days | bar: JAKARTA 3 to JAKARTA 5
| Total | 41 | Days

## Master
CATEGORY | CATEGORY | COMPONENT COST
Equipment, Tools and Materials | Equipment, Tools and Materials | Balok
Handling, Permits, and Formalities | Equipment, Tools and Materials | Container Rental
Land Transportation | Equipment, Tools and Materials | Crane 100T
Sea Freight | Equipment, Tools and Materials | Crane 150T
| Equipment, Tools and Materials | Crane 200T
| Equipment, Tools and Materials | Crane 10T
| Equipment, Tools and Materials | Crane 50T
| Equipment, Tools and Materials | Crane 75T
| Equipment, Tools and Materials | Demob Cost Crane
| Equipment, Tools and Materials | Demob Cost Forklift
| Equipment, Tools and Materials | Demob Cost Jacking
| Equipment, Tools and Materials | Demob Cost Multiaxle
| Equipment, Tools and Materials | Fly Over Bridge
| Equipment, Tools and Materials | Forklift 10T
| Equipment, Tools and Materials | Forklift 15 T
| Equipment, Tools and Materials | Forklift 2.5T
| Equipment, Tools and Materials | Forklift 25T
| Equipment, Tools and Materials | Forklift 50T
| Equipment, Tools and Materials | Forklift 5T
| Equipment, Tools and Materials | Forklift 75T
| Equipment, Tools and Materials | Fuels
| Equipment, Tools and Materials | H Beam
| Equipment, Tools and Materials | Jacking Tools
| Equipment, Tools and Materials | Lashing
| Equipment, Tools and Materials | Mob Cost Crane
| Equipment, Tools and Materials | Mob Cost Forklift
| Equipment, Tools and Materials | Mob cost Jacking
| Equipment, Tools and Materials | Mob Cost Multiaxle
| Equipment, Tools and Materials | Multiaxle
| Equipment, Tools and Materials | Loading / Unloading
| Equipment, Tools and Materials | Lashing Charge
| Equipment, Tools and Materials | Handling
| Equipment, Tools and Materials | Plate
| Equipment, Tools and Materials | Truck Crane
| Handling, Permits, and Formalities | Accomodation
| Handling, Permits, and Formalities | Air Ticket
| Handling, Permits, and Formalities | Communinty Coordination
| Handling, Permits, and Formalities | Custom Clearance
| Handling, Permits, and Formalities | Escort
| Handling, Permits, and Formalities | Fumigation
| Handling, Permits, and Formalities | Labour
| Handling, Permits, and Formalities | Operator
| Handling, Permits, and Formalities | OPP/OPT
| Handling, Permits, and Formalities | Handling Container
| Handling, Permits, and Formalities | Overtime
| Handling, Permits, and Formalities | Public Road Transport Ticket
| Handling, Permits, and Formalities | Retribusi
| Handling, Permits, and Formalities | Security
| Handling, Permits, and Formalities | Storage
| Handling, Permits, and Formalities | Supervisi
| Land Transportation | CDD
| Land Transportation | Driven
| Land Transportation | Flat Bed Trailer 20 Feet
| Land Transportation | Flat Bed Trailer 40 Feet
| Land Transportation | Fuso
| Land Transportation | Lowbed 20T
| Land Transportation | Lowbed 30T
| Land Transportation | Lowbed 40T
| Land Transportation | Lowbed 50T
| Land Transportation | Lowbed 60T
| Land Transportation | Lowbed 90T
| Land Transportation | Pickup
| Land Transportation | Selfloader
| Land Transportation | Towing Car
| Land Transportation | Lumpsum
| Land Transportation | Tronton
| Sea Freight | Breakbulk
| Sea Freight | Capt/Crew Incentives
| Sea Freight | Condition Survey
| Sea Freight | Container Vessel
| Sea Freight | Demurage
| Sea Freight | Fresh Water
| Sea Freight | Fuel Bunker
| Sea Freight | Lashing Survey
| Sea Freight | LCT
| Sea Freight | Roro
| Sea Freight | Sailing Permit (SIB)
| Sea Freight | Security
| Sea Freight | Ship Agency
| Sea Freight | Surveyor
| Sea Freight | Tug and Barge
| Sea Freight | Vessel Piloting