## CBU
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  | 100010089201 | Mob 2 x CAT 6030 Dismantle + Assembly |  |  | Somber |  | Binuang |  | 3578350000 | 0 |  |  |  | 2018-08-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-08-01 to 2018-09-29
[19 empty] | 2018-08-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Somber
| Dismantle Job | [9 empty] | 0
1 | Operator Crane Terex CK |  |  |  |  | 1000000 | 1 | 33 | Man / Day | 0.9222% | 33000000
2 | Helper Crane Terex CK |  |  |  |  | 250000 | 1 | 33 | Man / Day | 0.2306% | 8250000
4 | Rental Crane 60 ton |  | Equipment, Tools and Materials | Crane 50T |  | 900000 | 1 | 330 | Unit / Hours | 8.3% | 297000000
5 | Meal+Penginapan, Crew Crane, Rigger, Driver LV |  | Handling, Permits, and Formalities |  |  | 400000 | 8 | 33 | Person/day | 2.951% | 105600000
6 | Mob Crane 75 Ton |  | Equipment, Tools and Materials | Mob Cost Crane |  | 30000000 | 1 | 1 | Job/Trip | 0.8384% | 30000000
7 | Mob Crane 60 Ton |  | Equipment, Tools and Materials | Mob Cost Crane |  | 30000000 | 1 | 1 | Job/Trip | 0.8384% | 30000000
8 | Rigger |  | Handling, Permits, and Formalities | Operator |  | 500000 | 1 | 33 | Person/day | 0.4611% | 16500000
9 | Rental Manitou |  | Equipment, Tools and Materials | Forklift 10T |  | 450000 | 1 | 320 | Unit / Hours | 4.024% | 144000000
10 | Mob demob Manitou |  | Equipment, Tools and Materials | Mob Cost Forklift |  | 2500000 | 1 | 1 | Job/Trip | 0.06986% | 2500000
11 | Solar Crane Terex dan Solar Crane Sany |  |  |  |  | 15000 | 160 | 30 | Liter / Hari | 2.012% | 72000000
12 | Solar Manitou |  |  |  |  | 15000 | 30 | 30 | Liter / Hari | 0.3773% | 13500000
13 | Supervisi |  | Handling, Permits, and Formalities | Supervisi |  | 500000 | 2 | 33 | Person/day | 0.9222% | 33000000
14 | Tiket Pesawat |  | Handling, Permits, and Formalities | Air Ticket |  | 1800000 | 2 | 2 | Person/trip | 0.2012% | 7200000
15 | Rental Mobil + Fuel (Supervisi, Crew Crane dan Rigger) |  | Handling, Permits, and Formalities | Accomodation |  | 1000000 | 2 | 33 | Unit / Day | 1.844% | 66000000
Somber - Binuang
1 | Trucking 6030 dismantle |  | Land Transportation | Lowbed 40T |  | 40000000 | 4 | 2 | Unit / Trip | 8.943% | 320000000
|  |  | Land Transportation | Lowbed 30T |  | 35000000 | 3 | 2 | Unit / Trip | 5.869% | 210000000
|  |  | Land Transportation | Lowbed 20T |  | 28000000 | 2 | 2 | Unit / Trip | 3.13% | 112000000
|  |  | Land Transportation | Flat Bed Trailer 40 Feet |  | 25000000 | 6 | 2 | Unit / Trip | 8.384% | 300000000
2 | Tim Cobra |  | Handling, Permits, and Formalities |  |  | 250000 | 14 | 2 | Unit / Trip | 0.1956% | 7000000
Binuang
1 | Rental Crane 75 ton |  | Equipment, Tools and Materials | Crane 100T |  | 900000 | 1 | 504 | Unit / Hours | 12.68% | 453600000
2 | Rental Crane 50 ton |  | Equipment, Tools and Materials | Crane 50T |  | 900000 | 1 | 504 | Unit / Hours | 12.68% | 453600000
3 | Meal+Penginapan, Crew Crane, Rigger, Driver LV |  | Handling, Permits, and Formalities |  |  | 400000 | 8 | 42 | Person/day | 3.756% | 134400000
5 | Mob Crane 75 Ton |  | Equipment, Tools and Materials | Mob Cost Crane |  | 150000000 | 1 | 1 | Job/Trip | 4.192% | 150000000
6 | Mob Crane 50 Ton |  | Equipment, Tools and Materials | Mob Cost Crane |  | 30000000 | 1 | 1 | Job/Trip | 0.8384% | 30000000
9 | Rental Manitou from Balikpapan |  | Equipment, Tools and Materials | Forklift 10T |  | 500000 | 1 | 504 | Unit/ Month | 7.042% | 252000000
10 | Mob Demob Manitou |  | Equipment, Tools and Materials | Mob Cost Forklift |  | 55000000 | 1 | 1 | Job/Trip | 1.537% | 55000000
11 | Rigger |  | Handling, Permits, and Formalities | Operator |  | 500000 | 1 | 42 | Person/day | 0.5869% | 21000000
12 | MCU Crew Crane + Operator Manitau + Driver |  |  |  |  | 2500000 | 8 | 1 | Man / Job | 0.5589% | 20000000
13 | Supervisi |  | Handling, Permits, and Formalities | Supervisi |  | 500000 | 2 | 42 | Person/day | 1.174% | 42000000
14 | Tiket Pesawat |  | Handling, Permits, and Formalities | Air Ticket |  | 1800000 | 2 | 2 | Person/trip | 0.2012% | 7200000
15 | Rental LV + Fuel (Supervisi, Crew Crane dan Rigger) |  | Handling, Permits, and Formalities | Accomodation |  | 38000000 | 2 | 2 | Unit/ Month | 4.248% | 152000000
Terms & Condition
| * Terms of delivery | : DTD, CK ABN - CK MHU
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : 4 x 6030
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | :
| * Subject Bunker calculation at | :
| * Cost included | : Driver, Fuel, Escort Police,
| * Cost excluded | : Community at loa kulu (If Any), PPn, Overnight
| * Free Time Loading + Unloading | :
| * Demurrage Fee | :
| * Subject to Survey KM 38 (Petung) | :
COST BUILD UP

## Master (hidden)
CATEGORY | CATEGORY | COMPONENT COST
Equipment, Tools and Materials | Equipment, Tools and Materials | Balok
Handling, Permits, and Formalities | Equipment, Tools and Materials | Container Rental
Land Transportation | Equipment, Tools and Materials | Crane 100T
Sea Freight | Equipment, Tools and Materials | Crane 150T
| Equipment, Tools and Materials | Crane 200T
| Equipment, Tools and Materials | CRANE 25T
| Equipment, Tools and Materials | Crane 50T
| Equipment, Tools and Materials | Crane 75T
| Equipment, Tools and Materials | Demob Cost Crane
| Equipment, Tools and Materials | Demob Cost Forklift
| Equipment, Tools and Materials | Demob Cost Jacking
| Equipment, Tools and Materials | Demob Cost Multiaxle
| Equipment, Tools and Materials | Fly Over Bridge
| Equipment, Tools and Materials | Forklift 10T
| Equipment, Tools and Materials | Forklift 15 T
| Equipment, Tools and Materials | Forklift 2.5T
| Equipment, Tools and Materials | Forklift 25T
| Equipment, Tools and Materials | Forklift 50T
| Equipment, Tools and Materials | Forklift 5T
| Equipment, Tools and Materials | Forklift 75T
| Equipment, Tools and Materials | Fuels
| Equipment, Tools and Materials | H Beam
| Equipment, Tools and Materials | Jacking Tools
| Equipment, Tools and Materials | Lashing
| Equipment, Tools and Materials | Mob Cost Crane
| Equipment, Tools and Materials | Mob Cost Forklift
| Equipment, Tools and Materials | Mob cost Jacking
| Equipment, Tools and Materials | Mob Cost Multiaxle
| Equipment, Tools and Materials | Multiaxle
| Equipment, Tools and Materials | Plate
| Equipment, Tools and Materials | Truck Crane
| Handling, Permits, and Formalities | Accomodation
| Handling, Permits, and Formalities | Air Ticket
| Handling, Permits, and Formalities | Communinty Coordination
| Handling, Permits, and Formalities | Custom Clearance
| Handling, Permits, and Formalities | Escort
| Handling, Permits, and Formalities | Fumigation
| Handling, Permits, and Formalities | Labour
| Handling, Permits, and Formalities | Operator
| Handling, Permits, and Formalities | OPP/OPT
| Handling, Permits, and Formalities | Overtime
| Handling, Permits, and Formalities | Public Road Transport Ticket
| Handling, Permits, and Formalities | Retribusi
| Handling, Permits, and Formalities | Security
| Handling, Permits, and Formalities | Storage
| Handling, Permits, and Formalities | Supervisi
| Land Transportation | CDD
| Land Transportation | Flat Bed Trailer 20 Feet
| Land Transportation | Flat Bed Trailer 40 Feet
| Land Transportation | Fuso
| Land Transportation | Lowbed 20T
| Land Transportation | Lowbed 30T
| Land Transportation | Lowbed 40T
| Land Transportation | Lowbed 50T
| Land Transportation | Lowbed 60T
| Land Transportation | Lowbed 90T
| Land Transportation | Pickup
| Land Transportation | Selfloader
| Land Transportation | Towing Car
| Land Transportation | Tronton
| Sea Freight | Breakbulk
| Sea Freight | Capt/Crew Incentives
| Sea Freight | Condition Survey
| Sea Freight | Container Vessel
| Sea Freight | Demurage
| Sea Freight | Fresh Water
| Sea Freight | Fuel Bunker
| Sea Freight | Lashing Survey
| Sea Freight | LCT
| Sea Freight | Roro
| Sea Freight | Sailing Permit (SIB)
| Sea Freight | Security
| Sea Freight | Ship Agency
| Sea Freight | Surveyor
| Sea Freight | Tug and Barge
| Sea Freight | Vessel Piloting