## CBU
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Destination | Rev No | Total CBU Amount | Total Cost Actual |  |  |  | Estimate Start Execution Date : |  |  | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | 5X777 |  |  | BBE BAKUNGAN |  | BMB BINUANG |  | 581890000 | 0 |  |  |  | 2018-01-01
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[19 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| BBE, BAKUNGAN | [8 empty] | 0% | 0
| Supervisi | BBE | Handling, Permits, and Formalities | Supervisi |  | 500000 | 1 | 1 | person/day | 0.08593% | 500000
| Rental LV + Fuel | BBE | Handling, Permits, and Formalities |  |  | 1900000 | 1 | 1 | unit/day | 0.3265% | 1900000
| BBE BAKUNGAN - BMB BINUANG | [8 empty] | 0% | 0
| LCT |  | Sea Freight | LCT |  | 526240000 | 1 | 1 | LCT | 90.44% | 526240000
| Lashing Survey |  | Sea Freight | Lashing Survey |  | 15000000 | 1 | 1 | LCT | 2.578% | 15000000
| Ranmor |  | Sea Freight |  |  | 500000 | 5 | 1 | unit/trip | 0.4296% | 2500000
| BMB BINUANG | [8 empty] | 0% | 0
| Supervisi |  | Handling, Permits, and Formalities |  |  | 500000 | 1 | 3 | person/day | 0.2578% | 1500000
| Rental LV + Fuel |  | Handling, Permits, and Formalities |  |  | 1900000 | 1 | 3 | person/day | 0.9796% | 5700000
| PLN |  | Handling, Permits, and Formalities |  |  | 5000000 | 5 | 1 | person/day | 4.296% | 25000000
| Escort |  | Handling, Permits, and Formalities |  |  | 500000 | 5 | 1 | unit/trip | 0.4296% | 2500000
| akomodasi |  | Handling, Permits, and Formalities |  |  | 35000 | 30 | 1 | person/job | 0.1804% | 1050000
[10 empty] | 0% | 0
Terms & Condition
| * Terms of delivery | : DTD
| * LCT/Vessel Name & terms of LCT/Vessel | :
| * LCT will beaching at | :
| * Readiness of vessel/ETD Orig/ETA Dest | :
| * Subject to P.List | : Dump Truck 30 T
| * Subject to availability LCT/Vessel at | :
| * Subject to jetty/port/site condition | : Good
| * Subject to weather condition | : Good
| * Subject exchange Rate/BAF | : IDR 15.000,-
| * Subject to confirmation | :
| * Cost included | : Ship insurance, fuel.
| * Cost excluded | : Quantity and quality (marine and land) insurance, additional local charges, inspection, storage, demurrage, community issues, taxes,
| * Free Demurrage | : 4 days
| * Demurrage Fee | : Rp 25.000.000
| * Subject to safety max load | :
* Above rates quoted are applicable for general cargo only NOT applicable for DGR, PER, AVI, HUM, and DIP
* Above rates quoted which will be subject to the space availability
* Subject to local charges at origin and destination.
* Rates Quoted excludes other charges, if any, not specified aboveare subject to change with our without prior notice.
* Subject to carrier space and equipment availability.
* Above rates, exclude marine insurance, overtime, urgent delivery and special arrangement / requirements
* Above rates are subject to any duty / taxes at destination
* Rates are subject to any increase on inclusive charges where applicable.
* Rates are subject to any demurrage/additional charges at origin/destination due to shipper/consignee issue
* Charges quoted are inclusive of any regulation/requirement to adhere/complied with Singapore & Destination custom
* For customer's premises that do not permit fumigation, additional transportation & warehouse handling charges are applicable
Term & Condition Demurrage :
Demurrage apply since Vessel is ready at POL based on agreed Laycan
Demurrage apply on daily basis or 24 hours from 00.00 hrs -24.00 hrs
Demurrage remains apply which ever:
1. Port is not available due to queuing process.
2. Jetty's Master approval has not been released.
3. Loading / Unloading cannot be performed due to readiness of the stevedoring company.
4. Loading / Unloading time has exceed its free time.
5. Jetty's Authorized Personel is not available at the office due to National Holiday / Weekend.
6. Low/high tide or
7. Military activities occurance at the port.
COST BUILD UP

## Master
CATEGORY | CATEGORY | COMPONENT COST
Equipment, Tools and Materials | Equipment, Tools and Materials | Balok
Handling, Permits, and Formalities | Equipment, Tools and Materials | Container Rental
Land Transportation | Equipment, Tools and Materials | Crane 100T
Sea Freight | Equipment, Tools and Materials | Crane 150T
| Equipment, Tools and Materials | Crane 200T
| Equipment, Tools and Materials | Crane 10T
| Equipment, Tools and Materials | Crane 50T
| Equipment, Tools and Materials | Crane 75T
| Equipment, Tools and Materials | Demob Cost Crane
| Equipment, Tools and Materials | Demob Cost Forklift
| Equipment, Tools and Materials | Demob Cost Jacking
| Equipment, Tools and Materials | Demob Cost Multiaxle
| Equipment, Tools and Materials | Fly Over Bridge
| Equipment, Tools and Materials | Forklift 10T
| Equipment, Tools and Materials | Forklift 15 T
| Equipment, Tools and Materials | Forklift 2.5T
| Equipment, Tools and Materials | Forklift 25T
| Equipment, Tools and Materials | Forklift 50T
| Equipment, Tools and Materials | Forklift 5T
| Equipment, Tools and Materials | Forklift 75T
| Equipment, Tools and Materials | Fuels
| Equipment, Tools and Materials | H Beam
| Equipment, Tools and Materials | Jacking Tools
| Equipment, Tools and Materials | Lashing
| Equipment, Tools and Materials | Mob Cost Crane
| Equipment, Tools and Materials | Mob Cost Forklift
| Equipment, Tools and Materials | Mob cost Jacking
| Equipment, Tools and Materials | Mob Cost Multiaxle
| Equipment, Tools and Materials | Multiaxle
| Equipment, Tools and Materials | Loading / Unloading
| Equipment, Tools and Materials | Lashing Charge
| Equipment, Tools and Materials | Handling
| Equipment, Tools and Materials | Plate
| Equipment, Tools and Materials | Truck Crane
| Handling, Permits, and Formalities | Accomodation
| Handling, Permits, and Formalities | Air Ticket
| Handling, Permits, and Formalities | Communinty Coordination
| Handling, Permits, and Formalities | Custom Clearance
| Handling, Permits, and Formalities | Escort
| Handling, Permits, and Formalities | Fumigation
| Handling, Permits, and Formalities | Labour
| Handling, Permits, and Formalities | Operator
| Handling, Permits, and Formalities | OPP/OPT
| Handling, Permits, and Formalities | Handling Container
| Handling, Permits, and Formalities | Overtime
| Handling, Permits, and Formalities | Public Road Transport Ticket
| Handling, Permits, and Formalities | Retribusi
| Handling, Permits, and Formalities | Security
| Handling, Permits, and Formalities | Storage
| Handling, Permits, and Formalities | Supervisi
| Land Transportation | CDD
| Land Transportation | Driven
| Land Transportation | Flat Bed Trailer 20 Feet
| Land Transportation | Flat Bed Trailer 40 Feet
| Land Transportation | Fuso
| Land Transportation | Lowbed 20T
| Land Transportation | Lowbed 30T
| Land Transportation | Lowbed 40T
| Land Transportation | Lowbed 50T
| Land Transportation | Lowbed 60T
| Land Transportation | Lowbed 90T
| Land Transportation | Pickup
| Land Transportation | Selfloader
| Land Transportation | Towing Car
| Land Transportation | Lumpsum
| Land Transportation | Tronton
| Sea Freight | Breakbulk
| Sea Freight | Capt/Crew Incentives
| Sea Freight | Condition Survey
| Sea Freight | Container Vessel
| Sea Freight | Demurage
| Sea Freight | Fresh Water
| Sea Freight | Fuel Bunker
| Sea Freight | Lashing Survey
| Sea Freight | LCT
| Sea Freight | Roro
| Sea Freight | Sailing Permit (SIB)
| Sea Freight | Security
| Sea Freight | Ship Agency
| Sea Freight | Surveyor
| Sea Freight | Tug and Barge
| Sea Freight | Vessel Piloting

## Sheet1
Project | Operating Plan | Days |  | DESEMBER
|  |  |  | 1 | 2 | 3 | 4 | 5 | 7 | 8 | 9
4 x 777 + 1 x 14M BBE - BMB via LCT | BBE
| Prepare 4x777 + 1x14M at BBE | 1 | Days | bar: DESEMBER 1
| Driven 4x777 + 1x14M to jetty BBE | 1 | Days | bar: DESEMBER 1
| Loading 4x777 + 1x14M into LCT | 1 | Days | bar: DESEMBER 2
BBE - BMB
| Lashing unit at LCT | 1 | Days | bar: DESEMBER 2
| Sailing LCT from Port BBE - Port BMB | 4 | Days | bar: DESEMBER 3 to DESEMBER 7
BMB
| unLoading 4x777 + 1x14M from LCT | 1 | Days | bar: DESEMBER 7
| Driven 4x777 + 1x14M from jetty BMB to PIT BMB | 1 | Days | bar: DESEMBER 8