## Rekap (hidden)
| margin Transportasi |  | 13.22%
Proposal of Multi Axle for FL#1 Project |  |  | PACKAGE 1 (DIGESTER) |  | PACKAGE 2 (LIME KILN) |  | PACKAGE 3 (EVAPORATOR) |  |  |  | PACKAGE 4 (PIPE RACK)
|  |  | Option 1 (1 per 2 days) Quantity | Cost | Option 1 (1 per 2 days) Quantity | Cost | Option 1 Quantity | Cost | Option 2 Quantity | Cost | Option 1 Quantity | Cost
S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) |  | COOKING ( 5 UNITS) | IDR | LIME KILN ( 9 UNITS ) | IDR | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR | PIPE RACK (35 DAYS INTERNAL SHIFTING) | IDR
| NUMBER OF TRIP (Trip) |  | 5 | 15460000 | 9 | 102255555.5556 | 19 | 48326315.7895 | 19 | 48326315.7895 | 44 | 19161363.6364
1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE |  | 10 Axle | 77300000 | 10 Axle | 920300000 | 30 Axle | 918200000 | 30 Axle | 918200000 | 10 Axle | 843100000
2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE |  | 1 Unit | 149900000 | 1 Unit | 445400000 | 2 Unit | 452400000 | 2 Unit | 452400000 | 1 Unit | 540900000
3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE |  | 18 Unit | 0 | 18 Unit | 0 | 48 PCS | 0 | 48 PCS | 0 | 18 Unit | 0
4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE |  | 36 Unit | 0 | 36 Unit | 0 | 0 | 0 | 0 | 0 | 36 Unit | 0
5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE |  | 8 Person | 159100000 | 8 Person | 387200000 | 11 Person | 612800000 | 11 Person | 612800000 | 8 Person | 488700000
6 | FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation) |  | - |  | - |  | 2 Bridge | 0 | - | 0 | - | 0
7 | REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation) |  | - |  | - |  | - | 0 | 2 Bridge | 0 | - | 0
8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site |  | ATTACHED |  | ATTACHED |  | attached | 0 | attached | 0 | 10 DAYS | 0
9 | Mobilization time of equipment (Include assembling) |  | 0 |  | 10 Days |  | 1 Month | 0 | 2 Month | 0 | ATTACHED | 0
10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc |  | - |  | - |  |  | 0 |  | 0 | - | 0
11 | Lashing material
12 | Obstacle Handling (electricity Cable) | [6 empty] | 62300000 |  | 62300000 |  | 0
| Total Cost |  |  | 386300000 |  | 1752900000 |  | 2045700000 |  | 2045700000 |  | 1872700000
|  |  | 6057600000 | [6 empty] | Grand Total | 13.22% | 6057600000 | 5950000000
| Terms and condition | [8 empty] | cost | cost | 5256050000 | 5036050000 | -220000000
| *Exclude Heavy lift equipment for assembling Multi Axles |  |  |  |  | Equipment Require |  |  |  |  | bottom | 12.5% | 6006914285.7143 | 5755485714.2857 | 194514285.7143
| *Exclude Bridge Strengtening |  |  |  | Jan | 1 set Multi Axle | 1 Crew |  |  |  |  | 11.66% | 50685714.2857 |  | -56914285.7143
| *Exclude Heavy lift equipment for Bridge Strengthening |  |  |  | Feb - March | 1 set Multi Axle | 1 Crew |  |  |  |  | 8.678% | 5351100584.874
| *Coordination with Logging Truck at hauling road supported by customers |  |  |  | April | 1 set Multi Axle | 2 Crew |  |  |  | jembatan | 1600000000
[6 empty] | 1,5 set Multi Axle |  |  |  |  | EL TB | 1396000000
| Multiaxle Standby Rate | per day | 21500000 |  | May | 1 set Multi Axle | 3 Crew |  |  |  |  | 9053600000
| Multiaxle Monthly Rate | month | 645000000 |  |  | 2 set Multi Axle
Term of Payment Multiaxle FL1 project
| 1st Invoice |  | 40% | [5 empty] | 325000000
| 2nd Invoice |  | 15% | [5 empty] | 81250000
| 3rd Invoice |  | 15%
| 4th Invoice |  | 15%
| 5th Invoice |  | 15%
Term of Payment Bridge Reinforcement
| 1st Invoice (soil test, desain and drawing) |  | 50%
| 2nd Invoice (construction) |  | 30%
| 3rd Invoice (final deflection test) |  | 20%
| No. | Tools | Unit | Unit Rate (Rp.) per month
| 1 | Elephan Leg | Pcs | 6000000
Transfer Beam
| 2 | 6 meters | pcs | 6000000
| 3 | 9 meters | pcs | 13500000
| 4 | Mob-Demob | 1 Trailer | 100000000
Unit rate count when unit start mobilisasion

## Cst (hidden)
Proposal of Multi Axle for FL#1 Project |  | PACKAGE 1 (DIGESTER) |  | PACKAGE 2 (LIME KILN) |  | PACKAGE 3 (EVAPORATOR) |  |  |  | PACKAGE 4 (PIPE RACK)
|  | Option 1 (1 per 2 days) Quantity | Cost | Option 1 (1 per 2 days) Quantity | Cost | Option 1 Quantity | Cost | Option 2 Quantity | Cost | Option 1 Quantity | Cost
S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) | COOKING ( 5 UNITS) | IDR | LIME KILN ( 9 UNITS ) | IDR | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR | PIPE RACK (INTERNAL SHIFTING) | IDR
| NUMBER OF TRIP (Trip) | 5 | 13400000 | 9 | 88733333.3333 | 19 | 41936842.1053 | 19 | 41936842.1053 | 35 | 20902857.1429
1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE | 10 Axle | 67000000 | 10 Axle | 798600000 | 20 Axle | 796800000 | 20 Axle | 796800000 | 10 Axle | 731600000
2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE | 1 Unit | 130000000 | 1 Unit | 386500000 | 2 Unit | 392500000 | 2 Unit | 392500000 | 1 Unit | 469300000
3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE | 18 Unit | 0 | 18 Unit | 0 | 48 PCS | 0 | 48 PCS | 0 | 18 Unit | 0
4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE | 36 Unit | 0 | 36 Unit | 0 | 0 | 0 | 0 | 0 | 36 Unit | 0
5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE | 8 Person | 138000000 | 8 Person | 336000000 | 11 Person | 531750000 | 11 Person | 531750000 | 8 Person | 424000000
6 | FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation) | - |  | - |  | 2 Bridge |  | - | 0 | - | 0
7 | REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation) | - |  | - |  | - | 0 | 2 Bridge |  | - | 0
8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site | ATTACHED |  | ATTACHED |  | attached | 0 | attached | 0 | 10 DAYS | 0
9 | Mobilization time of equipment (Include assembling) | 0 |  | 10 Days |  | 1 Month | 0 | 2 Month | 0 | ATTACHED | 0
10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc | - |  | - |  |  | 0 |  | 0 | - | 0
11 | Lashing material | [9 empty] | 0
11 | Obstacle Handling (electricity Cable) | [5 empty] | 54000000 |  | 54000000
11 | Total Cost |  | 335000000 |  | 1521100000 |  | 1775050000 |  | 1775050000 |  | 1624900000
5256050000
| Terms and condition | Equipment Require
| *Exclude Fuel, Heavy lift equipment for assembling Multi Axles | Jan | 1 set Multi Axle | 1 Crew
| *Exclude Fuel for PrimeMover and Multi Axles | Feb - March | 1 set Multi Axle | 1 Crew |  | mob demob
| *Exclude Heavy lift equipment for assembling Fly Over Bridge | April | 1 set Multi Axle | 2 Crew |  | trailer | 50000000
| *Exclude Heavy lift equipment for Bridge Strengthening |  | 1,5 set Multi Axle |  |  | container | 30000000
| *Coordination with Logging Truck at hauling road supported by customers | May | 1 set Multi Axle | 3 Crew |  | tronton | 40000000
| *Exclude Elephan legs, if any minimal number is 48 piecies with price @ IDR 4.800.000 / month |  | 2 set Multi Axle
*Exclude 9 meter Transfer beam, if any minimal number is 24 piecies with price @ IDR 18.500.000 /month
| *Exclude 6 meter Transfer beam, if any minimal number is 36 piecies with price @ IDR 14.000.000 /month | elephan legs needs | Qty | cost
|  | mob demob trailer | 2 | 50000000 | 100000000
|  | elephan legs needs | 192
|  | own elephan legs | 18
|  | rent number | 174 | 3000000 | 522000000 | 43.5
[5 empty] | 622000000 | 24
|  | cost per piece |  |  | 3239583.3333 | 1332000000
|  | price per unit per month |  |  | 4800000 | 311111.1111
|  | margin |  |  | 32.51% | 7000000
233333.3333
|  | Transfer beam (9 meter) | Qty | cost |  | 18000000
|  | mob demob traeler | 2 | 50000000 | 100000000 | 600000
|  | Transfer beam needs | 24.3309 |  |  | 288000000
|  | rent number | 24 | 12000000 | 288000000
388000000
|  | cost per piece |  |  | 16166666.6667
|  | price per unit per month |  |  | 18500000
|  | margin |  |  | 12.61%
|  | Transfer beam (6 meter) | Qty | cost
|  | mob demob traeler | 2 | 50000000 | 100000000
|  | Transfer beam needs | 36.4964 |  |  | 288000000
|  | rent number | 36 | 8000000 | 288000000
388000000
|  | cost per piece |  |  | 10777777.7778
|  | price per unit per month |  |  | 14000000
|  | margin |  |  | 23.02%
Note on E32: Imam Supriyanto: Elephan legs + Plat 2 cm
Note on K32: Imam Supriyanto: Elephan legs + Plat 2 cm
Note on E41: Imam Supriyanto: Elephan legs + Plat 2 cm
Note on K41: Imam Supriyanto: Elephan legs + Plat 2 cm
Note on E50: Imam Supriyanto: Elephan legs + Plat 2 cm
Note on K50: Imam Supriyanto: Elephan legs + Plat 2 cm

## CBU PIPE RACK (hidden)
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Dest | Rev No | Total CBU Amount | Total Selling | Total Cost Actual |  |  | Estimate Start Execution Date : |  |  |  | Period Highlight: |  |  |  |  | 3 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | FL 1 PROJECT |  |  | FUTONG PORT |  | PT RAPP MILLS |  | 2335100000 | 2747176470.5882 | 0 |  |  | 2018-01-01
[10 empty] | Margin | 15%
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | UOM | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration |  | PERIODS | [59 empty] | Proposal of Multi Axle for FL#1 Project |  | PACKAGE 4
[83 empty] | Option 1 Quantity | Cost | time axis 2018-01-01 to 2018-03-01
[21 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25 | S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) | PIPE RACK (INTERNAL SHIFTING) | IDR
[21 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE
| MOBILIZATION | [9 empty] | 5.891% | 137550000 | [68 empty] | 2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE
| LOADING @JKT | [79 empty] | 3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift | 0.2784% | 6500000 | [68 empty] | 4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0 | [68 empty] | 5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.006424% | 150000 | [68 empty] | 6 | FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation)
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.006424% | 150000 | [68 empty] | 7 | REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation)
| LAND TRANSPORT | [79 empty] | 8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site
| TRAILER 40 FT |  |  |  |  | 45000000 | 2 | unit | 1 | trip | 3.854% | 90000000 | [68 empty] | 9 | Mobilization time of equipment (Include assembling)
| SPSI |  |  |  |  | 500000 | 2 | unit | 1 | trip | 0.04282% | 1000000 | [68 empty] | 10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 1 | unit | 750 | KM | 0.4175% | 9750000 | [68 empty] | 11 | Etc ________________
| PERSONNEL | [79 empty] | 11 | Total Cost
| OPERATOR + CREW (AIR TICKET) |  |  |  |  | 2000000 | 5 | person | 2 | trip | 0.8565% | 20000000
| SUPERVISI (AIR TICKET) |  |  |  |  | 2000000 | 1 | person | 5 | trip | 0.4282% | 10000000
| TIME CHARTER | [9 empty] | 89.5% | 2090000000
MULTI AXLE
| TIME CHARTER (axle) |  |  |  |  | 650000 | 10 | axle | 150 | day | 41.75% | 975000000
PRIME MOVER 6x4
| TIME CHARTER |  |  |  |  | 110000000 | 1 | unit | 5 | Month | 23.55% | 550000000
SUPPORT EQUIPMENT
| TURN TABLE/EXT BEAM |  |  |  |  | 0 | 1 | unit | 5 | month | 0% | 0
| ELEPHANT LEG |  |  |  |  | 0 | 0 | unit | 5 | month | 0% | 0
| MOB-DEMOB ELEPHANT LEG |  |  |  |  | 0 | 0 | unit | 5 | month | 0% | 0
| TRANSFER BEAM |  |  |  |  | 0 | 0 | unit | 5 | month | 0% | 0
| MOB-DEMOB TRANSFER BEAM |  |  |  |  | 0 | 0 | unit | 5 | month | 0% | 0
OPERATIONAL COST
| MESS |  |  |  |  | 5000000 | 1 | unit | 5 | Month | 1.071% | 25000000
| MEALS&INCENTIVE DRIVER,OPR,CREW |  |  |  |  | 63000000 | 1 | unit | 5 | Month | 13.49% | 315000000
| SEWA MOBIL |  |  |  |  | 15000000 | 2 | unit | 5 | Month | 6.424% | 150000000
PERSONNEL
| SUPERVISI |  |  |  |  | 500000 | 1 | person | 150 | day | 3.212% | 75000000
| PLANNER |  |  |  |  | 500000 | 1 | person | 0 | day | 0% | 0
| HSE |  |  |  |  | 500000 | 1 | person | 0 | day | 0% | 0
| AIR TICKET HSE |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 0 | trip | 0% | 0
| AIR TICKET PLANNER |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 0 | trip | 0% | 0
| DEMOBILIZATION | [9 empty] | 4.606% | 107550000
UNLOADING @JKT
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift | 0.2784% | 6500000
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.006424% | 150000
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.006424% | 150000
LAND TRANSPORT
| TRAILER 40 FT |  |  |  |  | 45000000 | 2 | unit | 1 | trip | 3.854% | 90000000
| SPSI |  |  |  |  | 500000 | 2 | unit | 1 | trip | 0.04282% | 1000000
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 1 | unit | 750 | KM | 0.4175% | 9750000
Terms & Condition
| * Terms of delivery DTD FOT | : DTP / DTP / FOT / FOB
* Heavy lift equipment for assembling and dismantling multi axles supported by customer
* Cost excluded PPn
COST BUILD UP

## CBU
[7 empty] | Time Frame | 4 | 1 | 3 | 2 |  | months
No | Operating Plan (Activity List) | Base Cost | Qty |  |  |  | UOM | Qty |  |  |  | UOM | Total Cost |  |  |  | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration | PERIODS
|  |  | Pipe Rack | Digester | Lime Kiln | Evaporator |  | Pipe Rack | Digester | Lime Kiln | Evaporator |  | Pipe Rack | Digester | Lime Kiln | Evaporator | [6 empty] | #REF! | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
| MULTI AXLE | [11 empty] | 731600000 | 67000000 | 798600000 | 796800000 | [66 empty] | Proposal of Multi Axle for FL#1 Project |  | PACKAGE 4
| MOBILISASI | [83 empty] | Option 1 (1 per 2 days) Quantity | Cost
| CRANE 50 T | 6500000 | 1 | 0 | 1 | 1 | unit | 1 | 1 | 1 | 1 | shift | 6500000 | 0 | 6500000 | 6500000 | [66 empty] | S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) | PIPE RACK (INTERNAL SHIFTING) | IDR
| MOB DEMOB CRANE | 0 | 1 | 0 | 1 | 1 | job | 1 | 1 | 1 | 1 | job | 0 | 0 | 0 | 0 | [67 empty] | NUMBER TRIP (TRIP) | 44
| LABOUR | 150000 | 1 | 0 | 1 | 1 | job | 1 | 1 | 1 | 1 | shift | 150000 | 0 | 150000 | 150000 | [66 empty] | 1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE | 10 Axle | 731600000
| SUPERVISI | 150000 | 1 | 0 | 1 | 1 | person | 1 | 1 | 1 | 1 | shift | 150000 | 0 | 150000 | 150000 | [66 empty] | 2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE | 1 Unit | 469300000
| TRAILER 40 FT | 50000000 | 2 | 0 | 2 | 2 | unit | 1 | 1 | 1 | 1 | trip | 100000000 | 0 | 100000000 | 100000000 | [66 empty] | 3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE | 18 Unit | 0
| TIME CHARTER | [11 empty] | 0 | 0 | 0 | 0 | [66 empty] | 4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE | 36 Unit | 0
| TIME CHARTER (axle) | 223333.3333 | 10 | 10 |  |  | axle | 120 | 30 |  |  | day | 268000000 | 67000000 | 0 | 0 | [66 empty] | 5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE | 8 Person | 424000000
| TIME CHARTER (axle) vendor | 650000 |  |  | 10 | 10 |  |  |  | 90 | 60 |  | 0 | 0 | 585000000 | 390000000
| EXT BEAM | 50000000 | 1 | 1 | 1 | 2 | unit | 5 | 1 | 3 | 2 | month | 250000000 |  |  | 200000000 | [66 empty] | 6 | FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation) | - | 0
| DEMOBILISASI | [11 empty] | 0 | 0 | 0 | 0 | [66 empty] | 7 | REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation) | - | 0
| TRAILER 40 FT | 50000000 | 2 | 0 | 2 | 2 | unit | 1 | 1 | 1 | 1 | trip | 100000000 | 0 | 100000000 | 100000000 | [66 empty] | 9 | Mobilization time of equipment (Include assembling) | 10 DAYS | 0
| CRANE 50 T | 6500000 | 1 | 0 | 1 | 0 | unit | 1 | 1 | 1 | 1 | shift | 6500000 | 0 | 6500000 | 0 | [66 empty] | 8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site | ATTACHED | 0
| MOB DEMOB CRANE | 0 | 1 | 0 | 1 | 0 | job | 1 | 1 | 1 | 1 | job | 0 | 0 | 0 | 0 | [66 empty] | 10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc | - | 0
| LABOUR | 150000 | 1 | 0 | 1 | 0 | job | 1 | 1 | 1 | 1 | shift | 150000 | 0 | 150000 | 0 | [66 empty] | 11 | Lashing Material
| SUPERVISI | 150000 | 1 | 0 | 1 | 0 | person | 1 | 1 | 1 | 1 | shift | 150000 | 0 | 150000 | 0 | [66 empty] | 14 | total
| PRIME MOVER 6x4 | [11 empty] | 469300000 | 130000000 | 386500000 | 392500000
MOBILISASI
| SPSI | 500000 | 1 | 0 | 1 | 1 | unit | 1 | 1 | 1 | 1 | trip | 500000 | 0 | 500000 | 500000
| DRIVEN PRIME MOVER (FUEL) | 13000 | 1 | 0 | 1 | 1 | unit | 750 | 750 | 750 | 750 | KM | 9750000 | 0 | 9750000 | 9750000
| TIME CHARTER | [11 empty] | 0 | 0 | 0 | 0
| TIME CHARTER | 110000000 | 1 | 1 | 1 | 1 | unit | 4 | 1 | 3 | 2 | Month | 440000000 | 110000000 | 330000000 | 220000000
| FUEL | 20000 | 1 | 1 | 1 | 2 | unit | 440 | 1000 | 1800 | 3800 | KM | 8800000 | 20000000 | 36000000 | 152000000
| DEMOBILISASI | [11 empty] | 0 | 0 | 0 | 0
| SPSI | 500000 | 1 | 0 | 1 | 1 | unit | 1 | 1 | 1 | 1 | trip | 500000 | 0 | 500000 | 500000
| DRIVEN PRIME MOVER (FUEL) | 13000 | 1 | 0 | 1 | 1 | unit | 750 | 750 | 750 | 750 | KM | 9750000 | 0 | 9750000 | 9750000
ELEPHANT LEG
MOBILISASI
| TRAILER 40 FT | 50000000 | 3 | 0 | 1 | 0 | unit | 1 | 1 | 1 | 1 | trip | 150000000 | 0 | 50000000 | 0
| TIME CHARTER | [11 empty] | 0 | 0 | 0 | 0
| TIME CHARTER | 0 | 140 | 16 | 36 | 124 | unit | 4 | 1 | 3 | 2 | Month | 0 | 0 | 0 | 0
| DEMOBILISASI | [11 empty] | 0 | 0 | 0 | 0
| TRAILER 40 FT | 50000000 | 3 | 0 | 1 | 0 | unit | 1 | 1 | 1 | 1 | trip | 150000000 | 0 | 50000000 | 0
TRANSFER BEAM
MOBILISASI
| TRONTON | 35000000 | 4 | 0 | 1 | 2 | unit | 1 | 1 | 1 | 1 | trip | 140000000 | 0 | 35000000 | 70000000
| TIME CHARTER | [11 empty] | 0 | 0 | 0 | 0
| TRANSFER BEAM 6 METER | 0 | 70 | 8 | 18 | 62 | unit | 4 | 1 | 3 | 2 | Month | 0 | 0 | 0 | 0
| DEMOBILISASI | [11 empty] | 0 | 0 | 0 | 0
| TRONTON | 35000000 | 4 | 0 | 1 | 2 | unit | 1 | 1 | 1 | 1 | trip | 140000000 | 0 | 35000000 | 70000000
| LABOUR | [11 empty] | 424000000 | 138000000 | 336000000 | 531750000
PERSONNEL
| MULTI AXLE CREW (AIR TICKET) | 2000000 | 5 | 5 | 5 | 5 | person | 2 | 0 | 1 | 1 | trip | 20000000 | 0 | 10000000 | 10000000
| MULTI AXLE CREW (AIR TICKET) add tim | 2000000 |  |  |  | 5 | person |  |  |  | 2 | trip | 0 | 0 | 0 | 20000000
| ADDITIONAL DRIVER + CREW (AIR TICKET) | 2000000 |  |  |  | 3 |  |  |  |  | 2 |  | 0 | 0 | 0 | 12000000
| MEALS&INCENTIVE MULTI AXLE | 65000000 | 1 | 1 | 1 | 1 | unit | 4 | 1 | 1 | 2 | Month | 260000000 | 65000000 | 65000000 | 130000000
| MEALS&INCENTIVE MULTI AXLE add tim | 65000000 |  |  |  | 1 | unit |  |  |  | 2 | Month | 0 | 0 | 0 | 130000000
| ADDITIONAL DRIVER + CREW (MEALS) | 33750000 |  |  |  | 1 | unit |  |  |  | 1 |  | 0 | 0 | 0 | 33750000
| SUPERVISI (AIR TICKET) | 2000000 | 1 | 1 | 1 | 1 | person | 2 | 0 | 1 | 1 | trip | 4000000 | 0 | 2000000 | 2000000
| SUPERVISI | 500000 | 1 | 1 | 1 | 1 | person | 120 | 30 | 90 | 60 | day | 60000000 | 15000000 | 45000000 | 30000000
| PLANNER | 500000 |  | 1 | 1 | 1 | person | 120 | 30 | 90 | 60 | day | 0 | 15000000 | 45000000 | 30000000
| HSE | 500000 |  | 1 | 1 | 1 | person | 120 | 30 | 90 | 60 | day | 0 | 15000000 | 45000000 | 30000000
| AIR TICKET HSE | 2000000 | 1 | 1 | 1 | 1 | person | 0 | 2 | 1 | 1 | trip | 0 | 4000000 | 2000000 | 2000000
| AIR TICKET PLANNER | 2000000 | 1 | 1 | 1 | 1 | person | 0 | 2 | 1 | 1 | trip | 0 | 4000000 | 2000000 | 2000000
| OPERATIONAL COST | [11 empty] | 0 | 0 | 0 | 0
| MESS | 5000000 | 1 | 1 | 2 | 2 | unit | 4 | 1 | 3 | 2 | Month | 20000000 | 5000000 | 30000000 | 20000000
| MESS add tim | 5000000 |  |  |  | 2 | unit |  |  |  | 2 | Month | 0 | 0 | 0 | 20000000
| SEWA MOBIL | 15000000 | 1 | 1 | 2 | 2 | unit | 4 | 1 | 3 | 2 | Month | 60000000 | 15000000 | 90000000 | 60000000
| OBSTACLE | [11 empty] | 0 | 0 | 0 | 54000000
| ELECTRICITY CABLE | [11 empty] | 0 | 0 | 0 | 0
| TEMPORARY REMOVAL | 54000000 |  |  |  | 1 |  |  |  |  | 1 |  | 0 | 0 | 0 | 54000000
[13 empty] | 1624900000 | 335000000 | 1521100000 | 1775050000
| Terms & Condition | [14 empty] | 5256050000
| * Terms of delivery DTD FOT | [14 empty] | 4819250000
| * Heavy lift equipment for assembling and dismantling multi axles supported by customer | [13 empty] | 12.5% | 5351100584.874
| * Cost excluded PPn | [14 empty] | 95050584.874
|  |  | ton |  |  |  | Per Trip |  |  | Per Set
| Mobilisasi |  | elephant leg | beam 6 | beam 9 |  | elephant leg | beam 6 | beam 9 | piperack*cooking | lime kiln | evaporator |  |  | 12.5% | 1600000000
| Trailer | 50000000 | 75 |  |  |  | 48 | 16 | 2 | 6 | 6 | 2 |  |  |  | 1400000000
| Container | 30000000 | 75 |  |  |  | 48 | 0 | 0 | 5 | 5 | 2
| Tronton | 40000000 | 75 |  |  |  | 36 | 0 | 0 | 4 | 4 | 2
| Unit Price | unit price vendor rental | qty | day | unit price/month | total unit price | unit harga fabrikasi per batang | unit harga fabrikasi per batang | total price |  |  |  | Lime Kiln | Evaporator | Unit rate | Pipe rack&Cooking Package | Lime Kiln | Evaporator
| Elephant Leg | 320000 | 192 | 30 | 9600000 | 9216000000 | 8000000 | 10000000 | 1920000000 | 66666.6667 |  | Elephant Leg | 4 | 8 | 277777.7778 | #REF! | 1111111.1111 | 2222222.2222
| Transfer Beam 6 meter | 320000 | 96 | 30 | 9600000 | 4608000000 | 12000000 | 12000000 | 1152000000 | 80000 |  | Beam 6 meter | 2 |  | 277777.7778 | #REF! | 555555.5556 | 0
| Transfer Beam 9 meter | 480000 | 192 | 30 | 14400000 | 5529600000 | 27000000 | 27000000 | 5184000000 | 450000 |  | Beam 9 meter |  | 16 | 465277.7778 | #REF! | 0 | 7444444.4444
[6 empty] | 19353600000 |  |  | 8256000000 | [6 empty] | #REF! | 1666666.6667 | 9666666.6667
[8 empty] | 77714285.7143 | [7 empty] | #REF! | 50000000 | 290000000
136000000
[10 empty] | 12 | 12
[9 empty] | 12 | 24 | 24 | 12
[11 empty] | 6 | 12
[10 empty] | 6 | 12
| cc | #012611
| bn | 100010090376

## CBU DIGESTER (hidden)
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Dest | Rev No | Total CBU Amount | Total Selling | Total Cost Actual |  |  | Estimate Start Execution Date : |  |  |  | Period Highlight: |  |  |  |  | 3 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | FL 1 PROJECT |  |  | FUTONG PORT |  | PT RAPP MILLS |  | 809100000 | 951882352.9412 | 0 |  |  | 2018-01-01
[10 empty] | Margin | 15%
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | UOM | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration |  | PERIODS | [59 empty] | Proposal of Multi Axle for FL#1 Project |  | PACKAGE 1
[83 empty] | Option 1 (1 per 2 days) Quantity | Cost | time axis 2018-01-01 to 2018-03-01
[21 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25 | S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) | COOKING ( 5 UNITS) | IDR
[21 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE (10 Axle) | 1 Set | 342800000
| MOBILIZATION | [9 empty] | 16.75% | 135550000 | [68 empty] | 2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE (6x4) | 1 Unit | 120750000
| LOADING @JKT | [79 empty] | 3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE | 10 | 6111111.1111
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift | 0.8034% | 6500000 | [68 empty] | 4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE | 20
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0 | [68 empty] | 5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE | 8 | 164000000
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.01854% | 150000 | [68 empty] | 6 | FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation) | 0
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.01854% | 150000 | [68 empty] | 7 | REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation) | 0
| LAND TRANSPORT | [79 empty] | 8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site
| TRAILER 40 FT |  |  |  |  | 45000000 | 2 | unit | 1 | trip | 11.12% | 90000000 | [68 empty] | 9 | Mobilization time of equipment (Include assembling) | 10 days
| SPSI |  |  |  |  | 500000 | 2 | unit | 1 | trip | 0.1236% | 1000000 | [68 empty] | 10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 1 | unit | 750 | KM | 1.205% | 9750000 | [68 empty] | 11 | Etc ________________
| PERSONNEL | [79 empty] | 11 | Total Cost
| OPERATOR + CREW (AIR TICKET) |  |  |  |  | 2000000 | 5 | person | 2 | trip | 2.472% | 20000000
| SUPERVISI (AIR TICKET) |  |  |  |  | 2000000 | 2 | person | 2 | trip | 0.9888% | 8000000
| TIME CHARTER | [9 empty] | 69.95% | 566000000
MULTI AXLE
| TIME CHARTER (axle) |  |  |  |  | 650000 | 10 | axle | 30 | day | 24.1% | 195000000
PRIME MOVER 6x4
| TIME CHARTER |  |  |  |  | 110000000 | 1 | unit | 1 | Month | 13.6% | 110000000
SUPPORT EQUIPMENT
| TURN TABLE/EXT BEAM |  |  |  |  | 50000000 | 1 | unit | 1 | month | 6.18% | 50000000
| TRANSFER BEAM |  |  |  |  | 5000000 | 15 | unit | 1 | month | 9.27% | 75000000
| ELEPHANT LEG |  |  |  |  | 1000000 | 25 | unit | 1 | month | 0%
OPERATIONAL COST
| MESS |  |  |  |  | 5000000 | 1 | unit | 1 | Month | 0.618% | 5000000
| MEALS&INCENTIVE DRIVER,OPR,CREW |  |  |  |  | 63000000 | 1 | unit | 1 | Month | 7.786% | 63000000
| SEWA MOBIL |  |  |  |  | 15000000 | 2 | unit | 1 | Month | 3.708% | 30000000
PERSONNEL
| SUPERVISI |  |  |  |  | 500000 | 2 | person | 30 | day | 3.708% | 30000000
| PLANNER |  |  |  |  | 500000 | 1 | person | 0 | day | 0% | 0
| HSE |  |  |  |  | 500000 | 1 | person | 0 | day | 0% | 0
| AIR TICKET HSE |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 2 | trip | 0.4944% | 4000000
| AIR TICKET PLANNER |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 2 | trip | 0.4944% | 4000000
| DEMOBILIZATION | [9 empty] | 13.29% | 107550000
UNLOADING @JKT
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift | 0.8034% | 6500000
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.01854% | 150000
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.01854% | 150000
LAND TRANSPORT
| TRAILER 40 FT |  |  |  |  | 45000000 | 2 | unit | 1 | trip | 11.12% | 90000000
| SPSI |  |  |  |  | 500000 | 2 | unit | 1 | trip | 0.1236% | 1000000
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 1 | unit | 750 | KM | 1.205% | 9750000
Terms & Condition
| * Terms of delivery DTD FOT | : DTP / DTP / FOT / FOB
* Heavy lift equipment for assembling and dismantling multi axles supported by customer
* Cost excluded PPn
COST BUILD UP

## CBU EVAPORATOR (hidden)
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Dest | Rev No | Total CBU Amount | Total Selling | Total Cost Actual |  |  | Estimate Start Execution Date : |  |  |  | Period Highlight: |  |  |  |  | 3 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | FL 1 PROJECT |  |  | FUTONG PORT |  | PT RAPP MILLS |  | #REF! | #REF! | 0 |  |  | 2018-01-01
[10 empty] | Margin | 15%
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | UOM | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration |  | PERIODS | [59 empty] | Proposal of Multi Axle for FL#1 Project |  | PACKAGE 3
[83 empty] | Option 1 Quantity | Cost | Option 2 Quantity | Cost | time axis 2018-01-01 to 2018-03-01
[21 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25 | S/N | SCOPE OF WORK (SHIFTING TO SITE 1 EQUIPMENT PER DAY) | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR | EVAPORATOR ( 18 UNITS ) - CRYSTALIZER (1 UNITS ) | IDR
[21 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 1 | NUMBER OF MULTI AXLE REQUIRED FOR EACH PACKAGE | 20 Axle
| MOBILIZATION | [10 empty] | 129550000 | [68 empty] | 2 | NUMBER OF PRIME MOVER REQUIRED FOR EACH PACKAGE | 2 Unit
| LOADING @JKT | [79 empty] | 3 | NUMBER OF TRANSFER BEAM REQUIRED FOR EACH PACKAGE
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift |  | 6500000 | [68 empty] | 4 | NUMBER OF ELEPHANT LEGS REQUIRED (EXCEPT EVAPORATOR) FOR EACH PACKAGE
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job |  | 0 | [68 empty] | 9 | Mobilization time of equipment (Include assembling)
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift |  | 150000 | [68 empty] | 5 | NUMBER OF LABOR REQUIRED BY LOGISTIC COMPANY FOR EACH PACKAGE | 11 Person
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift |  | 150000 | [68 empty] | 6 | OPT 1 :FLY OVER BRIDGE FOR EACH PACKAGE and time schedule (mobilization & installation) | 2 Bridge | 5000000000
| LAND TRANSPORT | [79 empty] | 9 | Mobilization time of equipment (Include assembling) | 1 Month
| TRAILER 40 FT |  |  |  |  | 50000000 | 2 | unit | 1 | trip |  | 100000000 | [68 empty] | 7 | OPT 2 :REINFORCEMENT BRIDGE FOR EACH PACKAGE and Time schedule (mobilization & installation) |  |  | 2 Bridge
| SPSI |  |  |  |  | 500000 | 2 | unit | 1 | trip |  | 1000000 | [68 empty] | 9 | Mobilization time of equipment (Include assembling) |  |  | 2 Month | 2500000000
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 1 | unit | 750 | KM |  | 9750000 | [68 empty] | 8 | TIME SCHEDULE ( FLEXIBLE) to shift package to site | Attached |  | Attached
| PERSONNEL | [79 empty] | 10 | Additional cost for Variance due to schedule delay, site not ready, clearance problem, etc
| OPERATOR + CREW (AIR TICKET) |  |  |  |  | 2000000 | 5 | person | 1 | trip |  | 10000000 | [68 empty] | 11 | Obstacle Coordination (electricity cable) |  | 100000000 |  | 100000000
| SUPERVISI (AIR TICKET) |  |  |  |  | 2000000 | 1 | person | 1 | trip |  | 2000000 | [68 empty] | 11 | Lashing Material
| ADDITIONAL OPERATOR + CREW (AIR TICKET) |  |  |  |  | 2000000 | 3 | person | 2 | trip |  | 12000000 | [68 empty] | 11 | Total Cost
| TIME CHARTER | [10 empty] | #REF!
MULTI AXLE A
| TIME CHARTER (axle) |  |  |  |  | 650000 | 20 | axle | 30 | day |  | 390000000
PRIME MOVER A
| TIME CHARTER |  |  |  |  | 110000000 | 2 | unit | 1 | Month |  | 220000000
MULTI AXLE B (MA+PM)
| TIME CHARTER (12 Axle) |  |  |  |  | 430000000 | 0 | unit | 1 | month |  | 0
SUPPORT EQUIPMENT
| EXT BEAM |  |  |  |  | 50000000 | 2 | unit | 1 | month |  | 100000000
| ELEPHANT LEG |  |  |  |  | 0 | 36 | unit | 1 | month |  | 0
| MOB DEMOB ELEPHANT LEG |  |  |  |  | 50000000 | 0 | unit | 2 | TRIP |  | 0
| TRANSFER BEAM |  |  |  |  | 0 | 18 | unit | 1 | month |  | 0
| MOB DEMOB TRANSFER BEAM |  |  |  |  | 50000000 | 0 | unit | 2 | TRIP |  | 0
OPERATIONAL COST
| MESS |  |  |  |  | 5000000 | 2 | unit | 1 | Month |  | 10000000
| MEALS&INCENTIVE DRIVER,OPR,CREW |  |  |  |  | #REF! | 2 | unit | 1 | Month |  | #REF!
| SEWA MOBIL |  |  |  |  | 15000000 | 2 | unit | 1 | Month |  | 30000000
| OBSTACLE (TEMPORARY DISMANTLE CABLE) |  |  |  |  | 100000000 | 1 | unit | 1 | job |  | 100000000
PERSONNEL
| SUPERVISI |  |  |  |  | 500000 | 1 | person | 30 | day |  | 15000000
| PLANNER |  |  |  |  | 500000 | 1 | person | 30 | day |  | 15000000
| HSE |  |  |  |  | 500000 | 1 | person | 30 | day |  | 15000000
| AIR TICKET HSE |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 1 | trip |  | 2000000
| AIR TICKET PLANNER |  | Land Transportation | Lowbed 30T |  | 2000000 | 1 | person | 1 | trip |  | 2000000
| DEMOBILIZATION | [10 empty] | 226750000
UNLOADING @JKT
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 1 | shift |  | 6500000
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job |  | 0
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift |  | 150000
| SUPERVISI |  |  |  |  | 100000 | 1 | person | 1 | shift |  | 100000
LAND TRANSPORT
| TRAILER 40 FT |  |  |  |  | 50000000 | 4 | unit | 1 | trip |  | 200000000
| SPSI |  |  |  |  | 500000 | 1 | unit | 1 | trip |  | 500000
| DRIVEN PRIME MOVER (FUEL) |  |  |  |  | 13000 | 2 | unit | 750 | KM |  | 19500000
Terms & Condition
| * Terms of delivery DTD FOT | : DTP / DTP / FOT / FOB
* Heavy lift equipment for assembling and dismantling multi axles supported by customer
* Cost excluded PPn
COST BUILD UP

## CBU FLY OVER BRIDGE (hidden)
|  |  | Booking Number | Project Name / Cargo |  |  | Origin |  | Dest | Rev No | Total CBU Amount | Total Selling | Total Cost Actual |  |  | Estimate Start Execution Date : |  |  |  | Period Highlight: |  |  |  |  | 3 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan)
|  |  |  | FL 1 PROJECT |  |  | FUTONG PORT |  | PT RAPP MILLS |  | 4179000000 | 4916470588.2353 | 0 |  |  | 2018-01-01
[10 empty] | Margin | 15%
[10 empty] | Time Frame | 4 | months
No | Operating Plan (Activity List) | Location | Cost Category | Component Cost | Additional Note | Base Cost | Qty | UOM | Qty | UOM | Cost Ratio / Activity | Amount Plan | Amount Actual | WO Number | Category Work Order | Plan Start | Plan Duration | Actual Start | Actual Duration |  | PERIODS
 | time axis 2018-01-01 to 2018-03-01
[21 empty] | 2018-01-01 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22 | 2017-08-23 | 2017-08-24 | 2017-08-25 | 2017-08-26 | 2017-08-27 | 2017-08-28 | 2017-08-29 | 2017-08-30 | 2017-08-31 | 2017-09-01 | 2017-09-02 | 2017-09-03 | 2017-09-04 | 2017-09-05 | 2017-09-06 | 2017-09-07 | 2017-09-08 | 2017-09-09 | 2017-09-10 | 2017-09-11 | 2017-09-12 | 2017-09-13 | 2017-09-14 | 2017-09-15 | 2017-09-16 | 2017-09-17 | 2017-09-18 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-09-22 | 2017-09-23 | 2017-09-24 | 2017-09-25
[21 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| MOBILIZATION | [9 empty] | 25.64% | 1071300000
LOADING @WAREHOUSE
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 6 | shift | 0.9332% | 39000000
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.003589% | 150000
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.003589% | 150000
SEA FREIGHT
| CONTAINER VESSEL |  |  |  |  | 15000000 | 48 | container | 1 | trip | 17.23% | 720000000
LAND TRANSPORT
| TRAILER 40 FT WAREHOUSE-PRIOK |  |  |  |  | 1500000 | 48 | UNIT | 1 | trip | 1.723% | 72000000
| TRAILER 40 FT PEKANBARU - SITE |  |  |  |  | 5000000 | 48 | UNIT | 1 | trip | 5.743% | 240000000
| TIME CHARTER | [9 empty] | 48.73% | 2036400000
FOB 32 METER SPAN
| TIME CHARTER |  |  |  |  | 400000000 | 2 | UNIT | 1 | MONTH | 19.14% | 800000000
FOB 43 METER SPAN
| TIME CHARTER |  |  |  |  | 600000000 | 2 | UNIT | 1 | MONTH | 28.72% | 1200000000
PERSONNEL
| SUPERVISI |  |  |  |  | 2000000 | 1 | person | 14 | day | 0.67% | 28000000
| MEALS |  |  |  |  | 600000 | 1 | person | 14 | day | 0.201% | 8400000
| DEMOBILIZATION | [9 empty] | 25.64% | 1071300000
LOADING @WAREHOUSE
| CRANE 50 T |  |  |  |  | 6500000 | 1 | unit | 6 | shift | 0.9332% | 39000000
| MOB DEMOB CRANE |  |  |  |  | 0 | 1 | job | 1 | job | 0% | 0
| LABOUR |  |  |  |  | 150000 | 1 | job | 1 | shift | 0.003589% | 150000
| SUPERVISI |  |  |  |  | 150000 | 1 | person | 1 | shift | 0.003589% | 150000
SEA FREIGHT
| CONTAINER VESSEL |  |  |  |  | 15000000 | 48 | container | 1 | trip | 17.23% | 720000000
LAND TRANSPORT
| TRAILER 40 FT WAREHOUSE-PRIOK |  |  |  |  | 1500000 | 48 | UNIT | 1 | trip | 1.723% | 72000000
| TRAILER 40 FT PEKANBARU - SITE |  |  |  |  | 5000000 | 48 | UNIT | 1 | trip | 5.743% | 240000000
Terms & Condition
| * Terms of delivery DTD FOT | : DTP / DTP / FOT / FOB
* Heavy lift equipment for assembling and dismantling multi axles supported by customer
* Cost excluded PPn
COST BUILD UP

## MA Schedule (hidden)
Activity Plan Mobilization of Cargo PT RAPP
No. | Activity |  | Jan | [29 empty] | Feb | [29 empty] | Maret | [29 empty] | April | [29 empty] | May
|  | PIC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Package 4 | DGE
| Pipe Rack Shipment | [7 empty] | 1 | 1 |  | 1 | 1 | [10 empty] | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | [5 empty] | 1 | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 1 | [7 empty] | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
| Package 1 | DGE
Cooking Shipment (Digester)
| Digester 15 | [44 empty] | 1 | 1
| Digester 16 | [46 empty] | 1 | 1
| Digester 17 | [50 empty] | 1 | 1
| Digester 18 | [53 empty] | 1 | 1
| Accumulator | [76 empty] | 1 | 1
Package 2
Lime Kiln Shipment
| Mobilization Lime Mud Filter from Futong Storage to Jobsite | [91 empty] | 1 | 1
| Mobilization Shell 1 from Futong Storage to Jobsite | [93 empty] | 1 | 1
| Mobilization Shell 2 from Futong Storage to Jobsite | [95 empty] | 1 | 1
| MobilizationShell 3 from Futong Storage to Jobsite | [97 empty] | 1 | 1
| Mobilization Shell 4 from Futong Storage to Jobsite | [99 empty] | 1 | 1
| Mobilization Shell 5 from Futong Storage to Jobsite | [101 empty] | 1 | 1
| Mobilization Shell 6 from Futong Storage to Jobsite | [103 empty] | 1 | 1
| Mobilization Shell 7 from Futong Storage to Jobsite | [105 empty] | 1 | 1
| Mobilization Cyclone from Futong Storage to Jobsite | [107 empty] | 1 | 1
Bridge Strengthening
Package 3
Evaporator Shipment
| Condensate Stripper column | [87 empty] | 1 | 1
[107 empty] | 1 | 1
| FF reflux tube evaporator | [89 empty] | 1 | 1
[109 empty] | 1 | 1
Tubel Element 1 C/D, group 1
[111 empty] | 1 | 1
Tubel Element 1 C/D, group 2
[113 empty] | 1 | 1
Tubel Element 1 C/D, group 3
[115 empty] | 1 | 1
Tubel Element 1 C/D, group 4
[117 empty] | 1 | 1
| Effect 1A | [117 empty] | 1 | 1
[119 empty] | 1 | 1
| Effect 1B | [119 empty] | 1 | 1
[121 empty] | 1 | 1
| Effect 2A | [121 empty] | 1 | 1
[123 empty] | 1 | 1
| Effect 2B | [123 empty] | 1 | 1
[125 empty] | 1 | 1
| Super Concentrator 1 A/B | [125 empty] | 1 | 1
[127 empty] | 1 | 1
| Effect 1 C/D | [127 empty] | 1 | 1
[129 empty] | 1 | 1
| Effect 3 | [129 empty] | 1 | 1
[131 empty] | 1 | 1
| Effect 4 | [131 empty] | 1 | 1
[133 empty] | 1 | 1
| Effect 5 | [133 empty] | 1 | 1
[135 empty] | 1 | 1
| Effect 6 | [135 empty] | 1 | 1
[137 empty] | 1 | 1
| Effect 7 | [137 empty] | 1 | 1
[139 empty] | 1 | 1
| Segregated Surface Condenser | [139 empty] | 1 | 1
[141 empty] | 1 | 1
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## Bridge Schedule (hidden)
Activity Plan Bridge Reinforcement PT RAPP
No. | Activity |  |  |  | Dec |  |  |  |  | Jan | [29 empty] | Feb | [29 empty] | Maret | [29 empty] | April
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Test
1 | Soil Test | bar: 23 to Jan 6
2 | Pemeriksaan khusus jembatan 1 (Selempaya Bridge) | bar: Dec 30 to Jan 6
Steel Material Test
Non Destructive Test Concrete (Hammer Test)
Concrete Rebar Detector Test
Deflection test before test
3 | Pemeriksaan khusus jembatan 2 (Pelalawan Bridge) | bar: Dec 30 to Jan 6
Steel Material Test
Non Destructive Test Concrete (Hammer Test)
Concrete Rebar Detector Test
Deflection test before test
4 | Desain dan Detail Drawing | bar: 23 to Jan 4
5 | Approval meeting | bar: Jan 5 to Jan 6
6 | Working preparation and permit | bar: 23 to Jan 6
7 | Construction Bridge 1 (24 m) | bar: Jan 7 to Feb 30
8 | Construction Bridge 2 (41 m) | bar: Feb 1 to Maret 30
Test
9 | Deflection test after reinforced and permit | bar: April 1 to April 7
10 | Ready to Use | bar: April 15
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Soil Test
Steel Material Test
Non Destructive Test Concrete (Hammer Test)
Concrete Rebar Detector Test
Deflection test before test
Deflection test after reinforced
17 jan digester datang

## CBU (2) (hidden)
No | Operating Plan (Activity List) | Base Cost | Qty
Pipe Rack
MULTI AXLE
MOBILISASI
| CRANE 50 T | 6500000 | 1 |  | 6500000
| MOB DEMOB CRANE | 0 | 1 |  | 0
| LABOUR | 150000 | 1 |  | 150000
| SUPERVISI | 150000 | 1 |  | 150000
| TRAILER 40 FT | 50000000 | 2 |  | 100000000
TIME CHARTER
| TIME CHARTER (axle) | 223333.3333 | 10
| TIME CHARTER (axle) vendor | 650000 | 300 | 195000000
| EXT BEAM | 50000000 | 1 | 50000000
| DEMOBILISASI |  |  | 0
| TRAILER 40 FT | 50000000 | 2 |  | 100000000 |  |  |  | 400000
| CRANE 50 T | 6500000 | 1 |  | 6500000
| MOB DEMOB CRANE | 0 | 1 |  | 0
| LABOUR | 150000 | 1 |  | 150000
| SUPERVISI | 150000 | 1 |  | 150000
| PRIME MOVER 6x4 |  |  | 0
| MOBILISASI |  |  | 0
| SPSI | 500000 | 1 |  | 500000
| DRIVEN PRIME MOVER (FUEL) | 20000 | 750 |  | 15000000
| TIME CHARTER |  |  | 0
| TIME CHARTER | 110000000 | 1 | 110000000
| FUEL | 20000 |  | 45000000
| DEMOBILISASI |  |  | 0
| SPSI | 500000 | 1 |  | 500000
| DRIVEN PRIME MOVER (FUEL) | 20000 | 750 |  | 15000000
| ELEPHANT LEG |  |  | 0
MOBILISASI
| TRAILER 40 FT | 50000000 | 3
TIME CHARTER
| TIME CHARTER | 0 | 140
DEMOBILISASI
| TRAILER 40 FT | 50000000 | 3
| TRANSFER BEAM |  |  | 0
MOBILISASI
| TRONTON | 35000000 | 4
TIME CHARTER
| TRANSFER BEAM 6 METER | 0 | 70
DEMOBILISASI
| TRONTON | 35000000 | 4
| LABOUR |  |  | 0
| PERSONNEL |  |  | 0
| MULTI AXLE CREW (AIR TICKET) | 2000000 | 5 |  | 10000000
| ADDITIONAL DRIVER + CREW (AIR TICKET) | 2000000
| MEALS&INCENTIVE MULTI AXLE | 65000000 | 1 | 65000000
| ADDITIONAL DRIVER + CREW (MEALS) | 33750000 | 0 | 0
| SUPERVISI (AIR TICKET) | 2000000 | 2 |  | 4000000
| SUPERVISI | 500000 | 30 | 15000000
| PLANNER | 500000 |  | 0
| HSE | 500000 |  | 0
| AIR TICKET HSE | 2000000 | 1 |  | 2000000
| AIR TICKET PLANNER | 2000000 | 1 |  | 2000000
| OPERATIONAL COST |  |  | 0
| MESS | 5000000 | 1 | 5000000
| SEWA MOBIL | 15000000 | 1 | 15000000
| OBSTACLE |  |  | 0
| ELECTRICITY CABLE |  |  | 0
| TEMPORARY REMOVAL | 54000000 |  | 0
|  |  |  | 500000000 | 155800000
| Terms & Condition |  |  | 16666666.6667 | 5193333.3333 |  |  |  | 5 | 3 | 2
| * Terms of delivery DTD FOT |  | 15% | 20000000 | 7000000 | daily standby rate |  |  | 2945000000 | 1767000000 | 1178000000 | 5890000000
| * Heavy lift equipment for assembling and dismantling multi axles supported by customer |  |  | 589000000 | 184000000 | monthly rate |  |  | 184000000 | 184000000 | 184000000 | 552000000
| * Cost excluded PPn |  |  |  |  | term of payment | [5 empty] | 6442000000
|  |  | ton |  | invoice 1 |  | 40% | 50% |  |  |  | 645000000 | 21500000
| Mobilisasi |  | elephant leg |  | invoice 2 |  | 15% | 30% |  |  |  | 5036050000
| Trailer | 50000000 | 75 |  | invoice 3 |  | 15% | 20%
| Container | 30000000 | 75 |  | invoice 4 |  | 15% |  |  |  |  | 595000000
| Tronton | 40000000 | 75 |  | invoice 5 |  | 15%
| Unit Price | unit price vendor rental | qty
| Elephant Leg | 320000 | 192
| Transfer Beam 6 meter | 320000 | 96
| Transfer Beam 9 meter | 480000 | 192

## CBU Elphn leg & beam (hidden)
TOOLS NEED ESTIMATED BY CKB
No. | Package | Qty (unit) | Duration (Month) | Duration |  |  | Rental Rate |  |  |  | Own Equipment
|  |  |  | Start | End | days | Unit Rate | daily base | Total |  | Qty (unit) | Unit Rate | Total
1 | Digester (pack. 1) | [13 empty] | 4000000 | 133333.3333
| Elephan leg | 8 | 2 | 2019-01-17 | 2019-02-19 | 33 | 4000000 | 220000 | 64000000 | 58080000 | 12 | 10000000 | 120000000 |  | 5000000 | 166666.6667
|  | 4 | 1 | 2019-03-17 | 2019-03-21 | 4 | 4000000 | 220000 | 16000000 | 3520000
| TB 6 meter |  | 2 |  |  |  | 5000000 |  | 0 |  |  | 12000000 | 0 |  | 13500000 | 450000
| TB 9 meter |  | 2 |  |  |  | 13500000 |  | 0 |  |  | 27000000 | 0 |  | 100000000 | 3333333.3333
2 | Lime Kiln (Pack. 2) | [11 empty] | 0
| Elephan leg | 24 | 2 | 2019-03-21 | 2019-04-30 | 40 | 4000000 | 220000 | 192000000 | 211200000 | 6 | 10000000 | 60000000
[6 empty] | 0 |  |  |  |  | 18 |  | 0
| TB 6 meter | 18 | 2 | 2019-03-21 | 2019-04-30 | 40 | 5000000 | 250000 | 180000000 | 180000000 | 18 | 12000000 | 216000000
| TB 9 meter |  | 2 |  |  |  | 13500000 |  | 0 |  |  | 27000000 | 0
3 | Evaporator (Pack. 3) | [11 empty] | 0
| Elephan leg |  | 2 |  |  |  | 4000000 |  | 0 |  |  | 10000000 | 0
| TB 6 meter |  | 2 |  |  |  | 5000000 |  | 0 |  |  | 12000000 | 0 |  | 12.39%
| TB 9 meter | 16 | 2 | 2019-04-16 | 2019-05-31 | 45 | 13500000 | 550000 | 432000000 | 396000000 | 6 | 27000000 | 162000000 | 1 | 2019-01-17 | 2019-02-19 | 33 | 24750000
|  | 15 | 1 | 2019-05-01 | 2019-05-31 | 30 | 13500000 | 550000 | 202500000 | 247500000 |  | 27000000 | 0 | 2 | 2019-03-17 | 2019-03-21 | 4 | 16500000
[11 empty] | 25 | 11000000 | 275000000 | 3
4 | Pipe rack (pack. 4) | [11 empty] | 0
| Elephan leg |  | 2 |  |  |  | 4000000 |  | 0 |  |  | 10000000 | 0
| TB 6 meter |  | 2 |  |  |  | 5000000 |  | 0 |  |  | 12000000 | 0
| TB 9 meter |  | 2 |  |  |  | 13500000 |  | 0 |  |  | 27000000 | 0
5 | Mob - Demob | 3 |  |  |  |  | 100000000 |  | 300000000 | 300000000 |  | 80000000 | 240000000
[9 empty] | 1386500000 | 1396300000 |  |  | 1073000000
The needs of Elephan Legs (EL) and Transfer Beam (TB) Assumption : | [11 empty] | Margin | 22.61%
EL and TB for Pipe rack will prepare by RAPP
Quantity of using EL and TB will recalculate furthere more after detil schedule was made
Minimal rental time is 2 months
Option Price Without the Elephant Legs
No. | Package | Qty (unit) | Duration (Month) |  |  |  | Rental Rate |  |  |  |  | Own Equipmt
[7 empty] | Unit Rate | daily base | Total | Total |  | Unit Rate | Total
1 | Lime Kiln (Pack. 2)
| TB 6 meter | 18 | 2 | 2019-03-21 | 2019-04-30 | 40 | 5000000 | 250000 | 180000000 | 180000000 | 18 | 12000000 | 216000000
2 | Evaporator (Pack. 3) | [11 empty] | 0
| TB 9 meter | 16 | 2 | 2019-04-16 | 2019-05-31 | 45 | 13500000 | 550000 | 432000000 | 396000000 | -9 | 27000000 | -243000000
|  | 15 | 1 | 2019-05-01 | 2019-05-31 | 30 | 13500000 | 550000 | 202500000 | 247500000 | 25 | 8000000 | 200000000
3 | Mob - Demob | 2 |  |  |  |  | 100000000 |  | 200000000 | 200000000 | 2 | 80000000 | 160000000
[9 empty] | 1014500000 | 1023500000 |  | 12000000 | 333000000
[12 empty] | Margin | 67.18%
Note on M12: Imam Supriyanto: Existing CKB
Note on M18: Imam Supriyanto: New
Note on M20: Imam Supriyanto: Modification
Note on M41: Imam Supriyanto: New
Note on M42: Imam Supriyanto: Modification

## Elphn leg & beam (hidden)
MOBILIZATION CAPACITY & PRICE
No. | Mobilization Mode | Price | Unit capacity Per Trip base on
|  |  | Weight (Ton) |  |  | Volume (Cbm)
|  |  | elephant leg | beam 6 (m) | beam 9 (m) | elephant leg | beam 6 (m) | beam 9 (m)
1 | Trailer | 50000000 | 60 |  |  | 48 | 50 | 32 | 0.6
2 | Container | 30000000 | 60 |  |  | 48 | 0 | 0 | 11.6667
3 | Tronton | 40000000 | 60 |  |  | 36 | 0 | 0
NUMBER OF TOOLS NEED PER CARGO
No. | Number of tools need | vol Cargo | elephant leg | beam 6 (m) | beam 9 (m)
1 | Pipe rack | 44 | 4 | 2
2 | Digester (cooking) | 5 | 4 | 2
3 | Lime Kiln | 9 | 4 | 2
4 | Evaporator | 18 | 8 |  | 12
RENTAL UNIT PRICE VENDOR VS BEP OF OWN ON EQUIPMENT
No. | Tools required | Rent. Unit Cost (Rp.) |  | Own Equipt. | BEP Own Eqpt. |  | Price Setting
|  | day | Month |  | days | Months |  | Min. Month | dayli rent
1 | Elephant Leg | 320000 | 9600000 | 10000000 | 31.25 | 1.0417 | 192000 | 1.6667 | 200000
2 | Transfer Beam
| 6 meters beam | 320000 | 9600000 | 12000000 | 37.5 | 1.25 | 160000 | 2 | 200000
| 9 meters beam | 480000 | 14400000 | 27000000 | 56.25 | 1.875 | 240000 | 2 | 450000
UNIT RATE
No. | Tools | Unit | Unit Rate (Rp.) per month |  | 20%
1 | Elephan Leg | Pcs | 6000000
2 | Transfer Beam
| 6 meters | Pcs | 6000000
| 9 meters | Pcs | 13500000
3 | Mob-Demob | Trailer | 100000000
cooking dan evap dari vendor
ALL TOOLS NEED
No. | Package | Unit | Total Qty (unit) |  |  |  | Duration (Month) | Total (Rp.)
|  |  | Elephan Leg | Transfer Beam |  | Mob - Demob |  | Elephan Leg | Transfer Beam |  | Mob-Demob | Total
|  |  |  | 6 meters | 9 meters |  |  |  | 6 meters | 9 meters
1 | Pipe rack | 44 | 176 | 88 |  | 8 | 5 | 5279999999.9994 | 2640000000 | 0 | 800000000 | 8719999999.9994
2 | Digester (cooking) | 5 | 20 | 10 |  | 1 | 3 | 360000000 | 180000000 | 0 | 100000000 | 640000000
3 | Lime Kiln | 9 | 36 | 18 |  | 2 | 2 | 432000000 | 216000000 | 0 | 200000000 | 848000000
4 | Evaporator Owos | 12 | 96 |  | 144 | 5 | 1 | 575999999.9999 | 0 | 1944000000 | 500000000 | 3019999999.9999
| Evaporator Heavy | 9 | 72 |  | 108 | 4 | 1 | 432000000 | 0 | 1458000000 | 400000000 | 2290000000
|  |  | 400 | 116 | 252 | 20 |  | 7079999999.9992 | 3036000000 | 3402000000 | 2000000000 | 15517999999.9992
TOOLS NEED ESTIMATED BY BELAWAN INDAH
No. | Package | Unit | Total Qty (unit) |  |  |  | Duration (Month) | Total (Rp.)
|  |  | Elephan Leg | Transfer Beam |  | Mob - Demob |  | Elephan Leg | Transfer Beam |  | Mob-Demob | Total
|  |  |  | 6 meters | 9 meters |  |  |  | 6 meters | 9 meters
1 | Pipe rack (pack. 4) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2 | Digester (pack. 1) |  | 24 | 0 | 0 | 1 | 1 | 144000000 | 0 | 0 | 100000000 | 244000000
3 | Lime Kiln (Pack. 2) |  | 48 | 0 | 0 | 1 | 1 | 288000000 | 0 | 0 | 100000000 | 388000000
4 | Evaporator (Pack. 3) | 2.8235 | 140 |  | 48 | 5 | 1 | 839999999.9999 | 0 | 648000000 | 500000000 | 1987999999.9999
|  |  | 212 | 0 | 48 | 7 |  | 1271999999.9999 | 0 | 648000000 | 700000000 | 2619999999.9999
No. | Package | UnitCargo | Total Qty (unit)
|  |  | Elephan Leg | Transfer Beam |  | Mob - Demob
|  |  |  | 6 meters | 9 meters
1 | Pipe rack (pack. 4) | 0 | 0 | 0 |  | 0
2 | Digester (pack. 1) | 5 | 20 | 10 |  | 2
3 | Lime Kiln (Pack. 2) | 4 | 16 | 8 |  | 1
4 | Evaporator (Pack. 3) | 9 | 36 |  | 108 | 10
|  |  | 72 | 18 | 108 | 13
| Desc. | Dim. | FT per unit | Tot.Ton | CBM per unit | CBM
| Berat Hbeam 6m | (2x(2*(6x0,3x0,3)) | 2.256 | 40.608 | 2.16 | 38.88
| Berat Hbeam 9m | 1x(3*(9x0,3x0,3)) | 2.538 | 274.104 | 2.43 | 262.44
| Elephant leg | 1x1x1m | 0.5 | 36 | 1 | 72
| Total |  |  | 350.712 |  | 373.32
| Mobdemob : | Trailer 12 m | max 30 Ton | 11.6904 |  | 5.401
Total Trailer
| Mobdemob : |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Digester (pack. 1) | Elephan Leg |  | 20 | Total Trailer 1: 10; Total Trailer 2: 10
|  | Transfer Beam | 6 meters | 10 | Total Trailer 1: 5; Total Trailer 2: 5
|  | Transfer Beam | 9 meters | 0 | Total Trailer 1: 0; Total Trailer 2: 0
|  |  | Std max 30 Ton | TON | Total Trailer 1: 16.28; Total Trailer 2: 16.28
|  |  | Std max 72 CBM | CBM | Total Trailer 1: 20.8; Total Trailer 2: 20.8
| Lime Kiln (Pack. 2) | Elephan Leg |  | 16 | Total Trailer 1: 16
|  | Transfer Beam | 6 meters | 8 | Total Trailer 1: 8
|  | Transfer Beam | 9 meters | 0 | Total Trailer 1: 0
|  |  | Std max 30 Ton | TON | Total Trailer 1: 26.048
|  |  | Std max 72 CBM | CBM | Total Trailer 1: 33.28
| Evaporator (Pack. 3) | Elephan Leg |  | 36 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transfer Beam | 6 meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transfer Beam | 9 meters | 108 | 9 | 9 | 9 | 9 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Std max 30 Ton | TON | 27.342 | 27.342 | 27.342 | 27.342 | 30.456 | 30.456 | 30.456 | 30.456 | 30.456 | 30.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Std max 72 CBM | CBM | 30.87 | 30.87 | 30.87 | 30.87 | 29.16 | 29.16 | 29.16 | 29.16 | 29.16 | 29.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOOLS NEED ESTIMATED BY CKB
No. | Package | Qty (unit) | Duration (Month) | Rental Rate | Total Trailer 2: Own Equipmt
|  |  |  | Unit Rate | Total Trailer 1: Total; Total Trailer 2: Unit Rate; Total Trailer 3: Total
1 | Digester (pack. 1) |  |  |  | Total Trailer 1: 0; Total Trailer 5: 6000000
| Elephan leg | 24 | 4 | 6000000 | Total Trailer 1: 576000000; Total Trailer 2: 10000000; Total Trailer 3: 240000000; Total Trailer 5: 13500000
| TB 6 meter |  | 4 | 6000000 | Total Trailer 1: 0; Total Trailer 2: 12000000; Total Trailer 3: 0; Total Trailer 5: 100000000
| TB 9 meter |  | 4 | 13500000 | Total Trailer 1: 0; Total Trailer 2: 27000000; Total Trailer 3: 0
| Mob - Demob | 1 |  | 100000000 | Total Trailer 1: 100000000; Total Trailer 2: 70000000; Total Trailer 3: 70000000
2 | Lime Kiln (Pack. 2) |  |  | 0 | Total Trailer 1: 0
| Elephan leg | 48 | 2 | 6000000 | Total Trailer 1: 576000000; Total Trailer 2: 10000000; Total Trailer 3: 480000000; Total Trailer 4: set of evaporator; Total Trailer 5: 2
| TB 6 meter |  | 2 | 6000000 | Total Trailer 1: 0; Total Trailer 2: 12000000; Total Trailer 3: 0; Total Trailer 5: 13,5 jt x 2; Total Trailer 6: 27 jt x 1
| TB 9 meter |  | 2 | 13500000 | Total Trailer 1: 0; Total Trailer 2: 27000000; Total Trailer 3: 0; Total Trailer 4: 20; Total Trailer 5: 19.22%; Total Trailer 6: 19.22%; Total Trailer 7: 32; Total Trailer 8: 189000000
| Mob - Demob | 1 |  | 100000000 | Total Trailer 1: 100000000; Total Trailer 2: 70000000; Total Trailer 3: 70000000; Total Trailer 4: 25; Total Trailer 5: 18.43%; Total Trailer 6: 18.43%; Total Trailer 7: 25; Total Trailer 8: 125000000
3 | Evaporator (Pack. 3) |  |  | 0 | Total Trailer 1: 0; Total Trailer 4: 30; Total Trailer 5: 18.43%; Total Trailer 6: 18.43%; Total Trailer 8: 314000000
| Elephan leg | 16 | 2 | 6000000 | Total Trailer 1: 192000000; Total Trailer 2: 10000000; Total Trailer 3: 160000000; Total Trailer 4: 35; Total Trailer 5: 17.38%; Total Trailer 6: 17.38%; Total Trailer 8: 9812500
| TB 6 meter |  | 2 | 6000000 | Total Trailer 1: 0; Total Trailer 2: 12000000; Total Trailer 3: 0; Total Trailer 4: 40; Total Trailer 5: 17.38%; Total Trailer 6: 17.38%
| TB 9 meter | 32 | 2 | 13500000 | Total Trailer 1: 864000000; Total Trailer 2: 9812500; Total Trailer 3: 314000000; Total Trailer 4: 45; Total Trailer 5: 15.64%
| Mob - Demob | 2 |  | 100000000 | Total Trailer 1: 200000000; Total Trailer 2: 70000000; Total Trailer 3: 140000000; Total Trailer 4: 50; Total Trailer 5: 15.64%
4 | Pipe rack (pack. 4) | 0 | 2 | 0 | Total Trailer 1: 0; Total Trailer 4: 55; Total Trailer 5: 15.13%
| Elephan leg |  | 2 | 6000000 | Total Trailer 1: 0; Total Trailer 2: 10000000; Total Trailer 3: 0
| TB 6 meter |  | 2 | 6000000 | Total Trailer 1: 0; Total Trailer 2: 12000000; Total Trailer 3: 0
| TB 9 meter |  | 2 | 13500000 | Total Trailer 1: 0; Total Trailer 2: 27000000; Total Trailer 3: 0
| Mob - Demob | 0 |  | 100000000 | Total Trailer 1: 0; Total Trailer 2: 70000000
|  |  |  | 251000000 | Total Trailer 1: 2608000000; Total Trailer 2: 238000000; Total Trailer 3: 1474000000
43.48%
The needs of Elephan Legs (EL) and Transfer Beam (TB) Assumption : |  |  |  |  | Total Trailer 2: 108
EL and TB for Pipe rack will prepare by RAPP
EL and TB for Digester will prepare by CKB
For Lime Kiln cargo CKB will re usage ex Digester EL and TB, and add some remaining EL and TB
for Evaporator cargo CKB will re usage from ex Digester and Lime Kiln and add some remaining EL and TB
Minimal rental time is 2 months
The time usage and volume of using EL and TB will recalculate furthere more after actual cargo arrive or after detil schedule
Note on D67: Abdul Rouf: ada 2 titik Hbeam, masing-masing 2xHbeam 30*30
Note on E67: Abdul Rouf: =(1,128/12)*6*2*2 1,128 adalah berat per 12 m Hbeam. 2 adaah jumlah Hbeam tiap titik. 2 adalah jumlah titik skid
Note on D68: Abdul Rouf: ada 1 titik Hbeam, masing-masing 3xHbeam 30*30
Note on G87: Abdul Rouf: pertimbangan tinggi cargo

## MastSchedule (hidden)
SCHEDULE MULTI AXLE FL1 PROJECT
CRANE 600 T0N AND 500 TON INSTALLATION EVAPORATOR, COOKING & PIPE RACK PLAN
EQUIPMENT NAME | Jan | [28 empty] | Feb | [28 empty] | March | [30 empty] | April | [29 empty] | May
| 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
As per schedule
Multi axle - 1 = 4 months ( 7 jan - 11 May )
Multi axle - 1
Multi axle - 2 = 1,5 month ( 30 Mar - 18 May )
Multi axle - 3 = 1 month ( 15 Apr - 18 May )
Pipe Rack
Digester and Accumulator
Kiln
Evaporator and ECRP
Discharging Vessel